CAPACITY DEVELOPMENT STRATEGY Output 1 POLICY ADVICE	1

CAPACITY DEVELOPMENT STRATEGY Output 2 PREVENTIVE RESPONSE	4

CAPACITY DEVELOPMENT STRATEGY – Output 3 COMMUNITY EMPOWEMENT	8

CAPACITY DEVELOPMENT STRATEGY – Output 4 HWC AWARENESS/OUTREACH	12

# CAPACITY DEVELOPMENT STRATEGY Output 1: POLICY ADVICE

| CAPACITY DEVELOPMENT MATRIX FOCUS: HWC2 Output 1 (Coordination capacities of the Wildlife Department of the Ministry of Natural Resources and Tourism for the implementation of the national human-wildlife conflict management strategy are improved) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Phase: from July 2025 to June 2028 | INDIVIDUALS | ORGANISATIONS | SOCIETY |  |
|  | COMPETENCE DEVELOPMENT | ORGANISATIONAL DEVELOPMENT | DEVELOPMENT OF COOPEREATION SYSTEM | Development of enabling new frameworks |
| - STRENGTHS - WEAKNESSES - OPPORTUNITIES - THREATS (SWOT) IN THE AREA OF CONCERN | MNRT, TAWA, TANAPA, districts Strengths - Availability of staffs with profession (networking and programming) - Basic data analysis capacity exists. - Accessibility of GIS tools exist - Availability of experienced ground-truthing, survey and field data collection staffs Weakness - Insufficient funds for on-the-Job training - Inadequate skill in Advanced data Analysis - Inadequate skills in data integration (GIS layers and PAIS - Most of staffs are not aware of developed NHWCMS (also not approved) Opportunity - WD staff exist that can be trained. - Interest in staff in learning new tech exists. - Readiness of staff to get training in GIS - Limited access to updated software - Changes and innovations of technology overtime | Strengths - GIS laboratories exist - Effective Management of ICT Unit - HWC data collection system (PAIS) is operational - Storage Exits (eGA, DC) - Data visualisation system exist (TAI) - Basic GIS skills exisit Weakness - No strategy for centralisation of all national wildlife data - Inconsistent data reporting and visualization Opportunity - Data driven decision making Threats - Cybercrimes and malware against electronic system - Regular staff reallocation | Strengths - Change of Consolation regulation - Data integration from other sources - Streamline consolation regulation and PAIS - Finalize the development of NHWCMS - Availability of communication channels Weaknesses - Low motivation for data collection - High dependency of the data collectors and institutions Opportunity - Use of simple technology ie smart phone - Technical support from multi sectors - Availability of inclusive strategies Threats - Wildlife risk in attending Incidents - Low trust weaken collaboration |  |
| INITENDED CAPACITIES | Train (MNRT, TAWA, TAWIRI, TANAPA, NGORONGORO) - Introduction to GIS and RS - Effective Data collection Technics - Statistical Analysis for PAIS - PAIS administration and upgrading - Drone Image Processing - Integrating GIS Layers with PAIS Data - Remote Sensing Applications - Data validation and quality assurance | - Financial Resource capacity - Project coordination capacity - Refresher course on existing technologies for Wildlife management (AI etc) - WD Capacity for timely &reliable data report - WD capacity to collect accurate data to make informed decisions. - WD capacity to communicate findings from PAIS using visual technology and printing. |  |  |
| ACTIVITIES & HYPOTHESIS | - Mentoring on PAIS use administration - Training on GIS enables users to effectively utilize spatial data. - Linking with external organizations with GIS experience to strength internal capability - Training programs to improve data analysis skills, (statistical analysis and interpretation of PAIS data - Provide access to relevant tools and software for data analysis and interpretation. - Provide training programs on drone image processing. - Facilitate training skills in data integration (GIS & PAIS) - Develop user manuals and documentation for GIS and other relevant tools | - Facilitate the operationalization of GIS Lab for data analysis and mapping - Centralize Wildlife data from all MNRT Divisions to MNRT Central Database. - Develop capacity building for data management to staff from MNRT Divisions. - Upgrade PAIS to cover GIS aspects, statistics, and other global data. - Encourage the use of digital payment. - Connecting WD with tech organizations for training and software access. - SOP data collection - SOP Reporting | Understanding capacity DEVELOPMENT |  |
| INTERACTION WITH THE OTHER LEVELS |  |  |  |  |
| COMPLEMENTARY ACTIVITIES BY OTHER PROJECTS/ACTORS IN THE SAME LINE OF ACTION | TANAPA Geospatial Strategy 2025-2030 action areas implementation MNRT via Wildlife Division implementation of integrated live data dashboard for supporting response |  |  |  |

# CAPACITY DEVELOPMENT STRATEGY Output 2: PREVENTIVE RESPONSE

| CAPACITY DEVELOPMENT MATRIX FOCUS: HWC 2 Output 2 (The inter-institutional ability to react to imminent and acute human-wildlife conflicts is increased.) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Phase: From July 2025 to June 2028 | INDIVIDUALS | ORGANISATIONS | SOCIETY |  |
|  | COMPETENCE DEVELOPMENT | ORGANISATIONAL DEVELOPMENT | DEVELOPMENT OF COOPEREATION SYSTEM | ENABLING FRAMEWORK |
| - STRENGTHS - WEAKNESSES - OPPORTUNITIES - THREATS (SWOT) IN THE AREA OF CONCERN | Ranger & VGS Strength: - Experience with community and wildlife - Part of permanent system Weakness: - Not trained in SF+G - Mediation conflict - Frequently change in duty station or responsibility Opportunity: - Rangers are partially trained; only fine tuning required (certified for the work) - Guided by government SOP during operation Threat: - Abuse of power, Stress increase, life risk, turnover Farmers Strength: - Local knowledge of animal movement Weakness: - Not applying best practices on how to deal with HWC Opportunity: - Farmers can be trained as VGS - Willing to cooperate Threat: - Hostility towards TANAPA and TAWA - Not implementing best practices for safety | TAWA, TANAPA, District + TFS Strength: - Recognized as government representative institutions/authority In site (HWC hotspot areas) - Have some equipment and partially trained staff - Mandate to implement legal framework - Operate under certified framework Weakness: - Not enough budget: financial, personnel, equipment - No clear plan of action on HWC - Lack of data management and SOP Opportunity: - Guided by drafted NHWCMS - Intersectoral approach (agricultural sector, land & livestock) if well-coordinated or plan to implement best practices are put in place - Change of leadership Threat: - Competition for resources - Lack of accountability - Increased pressure from political leaders - Change of cadres Community: Weakness: Don’t apply incident reporting channels (Knowledge, some not aware and information reach wrong respondents) Opportunity: - Collection of data of incidences | Strength - Pool of expertise & impact on bigger geographic areas. Weaknesses - Willingness to cooperate is very low - Cooperation processes not established/trained - No framework for enforcing cooperation Opportunities - Optimization of resources - Intersectoral approach. Threats - Competition for resources - Lack of accountability | Strength NHWHS Zonal 8 strategy National log framework Weaknesses No action plan No funds allocated Opportunities Finalize development of w NHWCMS 2025 – 2035 |
| INITENDED CAPACITIES | Rangers & VGS - Capacitated on safe response, safeguards & gender, conflict mediation, innovative efficient methods, response (use of drones) - capacitate lead farmers to become VGS; 75 trained under HWC I - H/capacity for farmers and on best practices to minimize risks on HWC and incident reporting - H/capacity on data collection for PA movement patterns - H/capacity through updated training curricula on HWC | - Awareness on communication channel – incident reporting - Data management protocol and accurate incident record - Efficient system for reporting incidents - Use of innovative method on response and incident recording problem animal movement pattern | - Strengthen cooperation system through HWC joint action plan for response. - Inclusive steering, monitoring, and reporting for response. | - Reviewed NHWMS with consideration of S&G - Socialization of zonal 8 strategy of the reviewed NHWMS. - Review financial plan |
| ACTIVITIES & HYPOTHESIS | - Monitoring the use of introduced logbook - Equip RRT with tents, led flashlights, airhorns, cars, drones and motorcycles - Train rangers to run drones - Facilitate review of district level HWC action plan and response framework | - Facilitate review of district level HWC action plan and response framework - Document and distribute incident reporting framework reference to problem animal consolation regulation | - Facilitate review of district level HWC action plan and response framework | - Reviewed zonal 8 strategy, and NHWCMS - Zonal located partners – TANAPA, TAWA and TFS |
| INTERACTION WITH THE OTHER LEVELS | - Training of VGS and farmers on Gender and SF improves the organization's reputation and acceptance. - Awareness of best practices enabling effective implementation of zonal 8 and district action plan, NHWCMS | - Provision of equipment motivate ranger to respond - Action plan will enable cooperation among organizations and define responsibility for RRT. - Data management protocol will be enhanced | Shared pool of expertise will increase and improve service delivery to community facing HWC challenges and optimization of resource use | Joint HWC framework will define role of actor and ensure accountability |
| COMPLEMENTARY ACTIVITIES BY OTHER PROJECTS/ACTORS IN THE SAME LINE OF ACTION | - FZS support RRT training for rangers - Farmer certification for VGS by Regrow - Community Awareness on safe behavior by WWF, Honeyguide & PAMS - Awareness on land use planning process via WWF/FZS under KFW Financial support | - WWF/KFW Land use support enhancing coordinated response - KfW – Capacity for Operation TAWA, TANAPA. Equipment and infrastructure - WWF monitoring record/data of incidents RRT - FZS support Nyerere National Park with operations in the region and land use training |  | KfW: Analysis of Safeguards risks - code of conduct. |

# CAPACITY DEVELOPMENT STRATEGY Output 3: COMMUNITY EMPOWEMENT

| CAPACITY DEVELOPMENT MATRIX FOCUS: HWC2 Output 3: The capacity of village communities to implement gender-sensitive human-wildlife conflict management at village level is improved. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Phase: from July 2025 to June 2028 | INDIVIDUALS | ORGANISATIONS | SOCIETY |  |
|  | COMPETENCE DEVELOPMENT | ORGANISATIONAL DEVELOPMENT | DEVELOPMENT OF COOPEREATION SYSTEM | DEVELOPMENT OF ENABLING FRAMEWORKS |
| - STRENGTHS -Have Proficient skills and Knowledge to perform tasks - WEAKNESSES -Lack sufficient resources to undertake their assigned tasks -Poor commitment of financial equipment’s - OPPORTUNITIES Availability of multi-stakeholders/Actors to partner and implement their duties i.e NGOs, Companies. - THREATS -Partners/Actors policies and regulations that restricts supporting some of actors’ initiatives -Lack of sustainability initiatives due to the community's perception that HWC mgt if for the Government | Strengths -VSLAs members now have cultivated the habit of saving their money instead of spending each money they earn. - Willingness of VSLAs group members to save and learn from the group and mentors ie. CARE have produced solid and active groups with minimal absenteeism and withdraw. -Availability of Beekeeping Officers in three districts (TFS and DCs) -Availability of Community Development Officers -Availability of District Livestock officers -Availability of District Land Officers -Availability of Trade and Investment officers -Availability of Community based trainers Weakness -VSLAs members have limited recording keeping skills especially on documenting their shares, savings, attendances etc. - Group members still have little knowledge of entrepreneurship skills, business management and leadership to run their groups. - Some selected CBTs are illiterate hence fail to manage and lead the group effectively, ending up creating group tensions. Opportunity -VSLA group members have the opportunity to learn from themselves and improve performance within the district on issues of amount for saving, types of collective investments, earnings and expenditures, record keeping etc. Threats - Absentiseem from some VSLA members in the group lowers group’s shares and revenue and jeopardizes group’s stability. | Strength -Availability of VSLA technical staff from CARE -Establishment and continues support of innovation fund and collective investments is critical to groups' existence. -Availability of VSLA kit to all groups has enabled group saving Weakness - Lack of Jointly Back stopping monitoring by CARE in collaboration with CDOs to ensure groups’ stability and sustainability was not conducted as a result weakened group’s performance in saving and recording shares. -Lack of frequently engaging CDOs in CARE’s work jeopardize group stability and sustainability as groups still need close mentoring and supervision. -Groups have limited financial, record keeping and business management skills, especially on identifying business enterprises and their management. -One VSLA technical staff from CARE is insufficient to cover the whole Ruvuma landscape. Insufficient resources i.e fuel, vehicles, motorbikes -Lack of financial sustainability plan Opportunity -There is opportunity of group members to have exchange programs so as they learn from themselves such as linking those group that are top performers with low performers in order to cultivate inspiration i.e Liwale VSLA groups to learn from Namtumbo groups -Easy to provide and monitor services to the communities through well-organized government structures i.e District level/Ward or village level Threat -Lack of motivation by CDOs to mentor and monitor VSLAs groups performance -Interference of political interests against technical know-how i. election processes, visit of national political leaders | S-Cooperate with range of experts from various institutions or agencies or Doctors, agricultural marketing cooperatives societies (AMCOS) W-High level of ignorance that leads to rejection of some interventions O-Accessibility of various social Services by different actors to target group i.e Hospital, drones, vehicles, agri-inputs, VSLA Kits etc T-Highly vulnerable exposed to risks from project implementation in the area | -Gender and Development policy 2023 -WMA and Corridor Regulations of 2018 -Beekeeping Development Policy and strategy |
| INITENDED CAPACITIES | -Redo refresher training to selected CBTs to ensure good management of VSLAs. -Re-select qualified CBTs who are literate and influential in managing VSLA groups. -Refresher training to CDOs on VSLA management and mentoring of groups on digital platform “CHOMOKA” - Sensitize CDOs on their sense of ownership to the project, not abandon their responsibility to CARE only. Improved beekeeping best practice related to HWC by effective colonization, honey harvesting and honey value addition, i.e. honey collection point improvements, value addition and packaging, improve colonization close monitoring and follow ups etc. -Conduct training to VSLA members on saving culture, acquisition of loans, loan disbursement and repayment. -Enhanced knowledge on diversification of livelihood through baseline survey and identification of opportunities skills and basics management of HWC -Enhancement of capacity for value addition through the provision of beekeeping inputs i.e. honey processing machine and collection center -Empowerment on value addition skills and accessibility on market linkages -Enhanced District capacity on financial management, training on issues related to responding, mitigation and outreach programs for HWC - Capacity to install and do maintenance on beehive fences | -Conduct refresher training to VSLA groups on saving, loaning, business management, leadership and record keeping skills. -Conduct capacity development on entrepreneurship skills to VSLA groups and CBTs. -Capacitate VSLA groups on diversification of income generating activities via collective investment approach -Retrain VSLA groups on CHOMOKA platform HWC DISTRICT PLAN: -Improved accessibility of resources to the District, TAWA and TANAPA i.e fuel, motorcycles -Beekeeping groups capacitated on beekeeping best practices and inputs -Village government, VSLA, Farmers groups capacitated on issues related to mitigation and outreach programs for HWC -CAP Committees: Training on livelihood diversification | - Conduct numerous community dialogue on gender dynamics and GTA -Improved in coordination among VSLA groups to form SACCOS??? -Mobilized beekeeper's groups to access beekeeping inputs and market through TABEDO ,Kijiji cha Nyuki etc. -Enhance ownership and coordination of stakeholders' meetings on addressing HWC issues i.e Mitigation, VSLA, agri-practices and outreach program -Increased participation of women on HWC interventions i.e decision making implementation, dialogue at national level -Mobilized village government to integrate HWC issues in VGA meetings as key agenda | -Update District Action plan with gender lens -District Development Department -District Livestock Department District Natural Resources Department -District Communities Development Department Village Government |
| ACTIVITIES & HYPOTHESIS | OP Activities: - setting up VSLAs (min. 20) and guiding them and existing ones in operating -Beekeeping groups: strengthen capacity of group members including youth (internship for young people) for sustainability - Train VGS as TOTs on Social Safeguards and gender | -Regular training to CDOs on mobilizing, monitoring, cost analysis of business enterprises of VSLA groups -developing entrepreneurship skills (incl. business plan), diversification of income-generating activities e.g. capacity to produce various honey-derived products. -Enhance capacity of PAMS to implement barrier mitigations and menstrual hygiene to Ruvuma landscape for managing issues of HWC | -Improve collaboration with stakeholders such as NGOs on issues related to VSLA and gender ie. Care International, District etc. - Improve collaboration with stakeholders on issues related to Beekeeping. District, TABEDO.BKU etc -Improve coordination with the village government on issues of mitigation and others. -Improve coordination with conservation education institutions ie; Mweka, Pasiansi, CBCTC for TOTs training on gender and safeguard -Improve cooperation with District staff ie. DCDO, DALF, DGO etc |  |
| INTERACTION WITH THE OTHER LEVELS | -Training of VGS on SF and gender will improve community’s interrations and collaborations with VGS for rapid response of HWC incidences. -Provided with training on Beekeeping Best Practices, business management, entrepreneurship, awareness on mitigation measures, awareness on unpalatable crops -Foster women dialogue within conservation sector and making processes -Provision of beekeeping inputs to beekeeping officers and farmers | -Development of Updated HWC Action plan will attract other institutions and NGOs to support the district in their specific need or area of interest such as VSLAs, Response, Outreach, Mitigations and PAIS, . Eg. WWF via their Ruvuma Transboundary project (Darwin) and have an interest in supporting response activities. However, the District plan will direct whether to invest in that area or focus in another specific area more relevant. | -Improve coordination with other Actors in landscape dealing with for VSLA, microcredit, business and agriculture. -Develop a platform to discuss women and men in conservation issues via community dialogues. Which, improves collaboration between men and women in society. -Improves coordination meetings and collaborations initiatives amongst TAWA, TANAPA and District to Discuss response, mitigation outreach etc. | -District -National -District |
| COMPLEMENTARY ACTIVITIES BY OTHER PROJECTS/ACTORS IN THE SAME LINE OF ACTION |  | -PAMS Foundation; teach farmers on best agricultural practices, especially on planting chill etc. |  |  |

# CAPACITY DEVELOPMENT STRATEGY Output 4: HWC AWARENESS/OUTREACH

| CAPACITY DEVELOPMENT MATRIX FOCUS: HWC2 Output 4 (The capacities of the relevant institutions to implement MWC-related awareness-raising measures at national and district level are strengthened.) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Phase: from July 2025 to June 2028 | INDIVIDUALS | ORGANISATIONS | SOCIETY |  |
|  | COMPETENCE DEVELOPMENT | ORGANISATIONAL DEVELOPMENT | DEVELOPMENT OF COOPERATION SYSTEM | DEVELOPMENT OF ENABLING FRAMEWORK |
| - STRENGTHS | Education Experts Strength -Know the content - Can influence curricular content -Know the review process -Able to train/ put into practice Weakness -Very occupied and busy -Guided by institution -Have limited influence Opportunities -Knowledge inputs -Networking -Flexibility Threats -Limited time -Competitions with other experts -Payment | Training institutions (Mweka, Pasiansi, CBCTC) Strength -Networking -Know process& procedures -Know knowledge of the recipients -Have influence -Research skills Weakness -Slow processes - Lack of funds -Busy Opportunities -Connection with Government -Partnership with relevant institutions Threats -Interest driven -Timely restricted -Delegate to non-experts | Strength -Willingness to cooperate -Experts /pool Weakness -No financial resources - Opportunities - experts pool available and influential -needs are well known, specific updates -format for review -short- and long-term courses Threats -no direct gain, benefits for extra work on review and update -risk of the curricular to be adopted -financial dependency/ donors - | JET Strength -well established journalis and experst asociation Weakness -donor dependacy Opportunities -Increa repoutation by good reporting Threats -reporting agionst government -restricted by government wishes |
|  | Journalists Strength -Content creation -Reporting skills -Flexibility -Start interaction Weakness -Restricted by media houses -Litter information on HWC and gender -limited financial resources Opportunities -Influence society -Popular Threats -Influence society negatively | JET Strength -Influence on reporting -Networking to journalists and media houses -Trusted Weakness -Lack of financial resources -Short-term influence Opportunities -Awareness creation -Good Reputation Threats -Misinformation | Strength -well established -neutral perception -influence changes in media and journalists Weakness -short term -have experts based on the needs Opportunities -work country wide -have platform for exchange -can easly update to priorities Threats -no contsnt feedback btn ministry and organization -enforce the existing problem |  |
| - OPPORTUNITIES | Farmers Strength -Know the HWC situation -Well-integrated in the community -Local knowledge Weakness -Exposed to HWC -Limited resources -Limited capacity -Marginalized/remoteness Economic pressure Priority needs Opportunities -Ready to adopt changes -Willing to be trained Threats -Do not follow regulations (LUPs) -Conflict escalation -Political changes -Exposed to wildlife | MNRT sub-institutions Strength -Well-established institution -Support of laws -Influence range behaviors Weakness -Lack of funds -Priorities protection/wildlife Lack of awareness of LUPs Opportunities -Influence rangers -Collaborate with government and partners -Have a direct connection to communities -Use technology Threats -Uncontrolled HWC -Exposed to political priorities -Anger to community /grievances |  |  |
| INITENDED CAPACITIES | Education experts -Fund to address -Gaps in curriculum -Knowledge exchange -Better reporting skills on HWC -HWC and gender -Knowledge on animal behavior and --LUP -Journalist | Training institutions -have fund to review education materials -S+G in training materials -short term course and concept on S+G -TOTS -Established network of journalists -report on HWC | Education institutions -capacitate wildlife experts to know interest development, safeguard, and gender -reduce negative influence of HWC institutions on society -influence the JET perception and attitude towards HWC through media | - Better repitation of wildlife experts - Use media to improve HWC reporting |
| ACTIVITIES & HYPOTHESIS | Education experts -Create platform for S+G and networking Journalist -provide training on reporting skills and editors for better HWC understanding Give fund for regional research. Farmers -awareness campaign-posters and jingles, live radios -awareness and outreach meeting -grassroots comics | Education institutions and Outreach Programme TAWA/TANAPA -Finance Agreement with MWEKA for curriculum review of wildlife educational institutions and TAWA+ Tanapa Environmental clubs- Outreach programmes, guidelines, and TOT of update curricula on HWC Grant Agreement and expertise for JEA (Journalist Environment Association) HWC journalist training. - Strengthen the capacity of journalists, editors, and local media houses to effectively, accurately reporting hwc information. The news collected by journalists during the contract will be published via Kasuku newspaper and other social media. - Raise awareness of the local communities on issues and challenges related to HWC through publications Support Outreach program by Tawa, Tanapa, district support on HWC awareness on target villages and mass media. | Enhance capacity development and media |  |
| INTERACTION WITH THE OTHER LEVELS | Education experts Dependency on organization level and political decisions journalist -form strong political interest group -knowledge inputs from outside beneficiaries -connected to the government and their programs | Training institutions -influenced by government agenda, -curricula validated by the ministry -depend on knowledge of experts -train wide range of wildlife managers Journalists -cooperate with journalist and government regulations -spread knowledge, capacitate journalist | Training institutions -translate ministry strategies to the society - pick up the interest of the society JET -multply knowledge to experts and non -experts | Training institutions -set foundation for good practice in wildlife management JET Improve perception on society and generations -enable society to form opinion |
| COMPLEMENTARY ACTIVITIES BY OTHER PROJECTS/ACTORS IN THE SAME LINE OF ACTION |  | PAMS- education activities | REGROW, RTI, ECOWISE, |  |