Special Initiative "Tackling the Root Causes of Displacement – (Re)integrating Refugees"

TC module: 	Improved living conditions and psychosocial support in the context of flight and expulsion in South Sudan

Project number:	2021.4079.6

Submission of an offer for a stand-alone TC module

The TC module presented in the offer and its funding correspond to the most favourable relationship between the purpose pursued by the TC module and the means to be used after examination of alternative possibilities.

Table of contents

List of abbreviations	3

1.	Abstract	4

2.	Classification of the project	5

2.1	Classification of the module in the strategic reference framework	5

2.2	Other development measures in the specific area of intervention of the module	6

3.	Problem and potential analysis (related to the TC module)	7

4.	Objectives, impact hypotheses, indicators and partners of the TC module	10

4.1	Objectives, target groups, impact hypotheses and indicators	10

4.2	Sponsors and partner structure	12

5.	Design of the TC module	13

5.1	Methodological approach and duration	13

5.2	Ensuring the sustainable effectiveness of the measures (outcomes)	18

5.3	Partner services, combined financing	19

5.4	Order value and detailed cost estimate	19

6.	Assessment of the effects and risks of the module	19

6.1	Impact assessment	19

6.2	Assessment of the risks to the effectiveness of the module	21

6.3	Certificate	25

A	Grounds

A1	Impact matrix

A2	Logic of impact

A3	Cost representations

A4	Identifiers

A5	Overview map of the intervention zone of planned projects in South Sudan

A6	Overview map of the number of internally displaced persons and returnees per district

A7	In-depth environmental and climate assessment

A8	Integrated Peace and Conflict Assessment

# List of abbreviations

| CAMP | Comprehensive Agricultural Master Plan Comprehensive overall agricultural concept |
| --- | --- |
| C flat | Central Equatoria State State of Central Equatoria |
| EES | Eastern Equatoria State State of East Equatoria |
| FAO | Food and Agriculture Organisation Food and Agriculture Organization of the United Nations |
| FBS | Farmer Business School Agricultural School of Economics |
| IDPs | Internally Displaced Persons Internally displaced persons |
| IMC | International Medical Corps International Medical Corps |
| IOM | International Organisation for Migration International Organization for Migration |
| LNOB | Leave no one behind Leave no one behind |
| MAFS | Ministry of Agriculture and Food Security Ministry of Agriculture and Food Security |
| MHPSS | Mental Health and Psychosocial Support Mental health and psychosocial support |
| VSLA WHH | Village Savings and Loan Associations Village savings and credit associations Welthungerhilfe |
| WFP | World Food Programme United Nations World Food Programme |

# 1.	Abstract

| Module title | Improved living conditions and psychosocial support in the context of flight and expulsion |
| --- | --- |
| Sector | Peace and social cohesion |
| Program | Cancelled / stand-alone TC module |
| Strategic Reference | Objectives of the Special Initiative "Tackling the Root Causes of Displacement - (Re)integrating Refugees"; Guidelines of the German Federal Government "Preventing Crises, Resolving Conflicts, Building Peace"; BMZ 2030 Nexus and Peace Partnership |
| Module Objective | The nutritional, economic and psychosocial living conditions of returnees, internally displaced persons and members of host communities have improved. |
| Contribution to the national implementation of the 2030 Agenda | The 2030 Agenda at the national level is in preparation; Reference to international Agenda 2030: SDG 1, SDG 2, SDG 4, SDG 16 and SDG 5 |
| Core problem | Returnees, internally displaced persons and vulnerable members of the host communities are unable to make a living and thus secure their food. Their psychosocial stress is very high due to the ongoing experiences of violence and displacement. |
| Target groups | Returnees, internally displaced persons and host communities, focus on women and young adults in Eastern and Central Equatoria |
| Lead executing agency | No sponsor on BMZ's instructions, implementation far from the government |
| Methodological approach (incl. instruments) | Increasing the production, diversity and quality of high-quality food and advising on improved nutrition. Education and skills measures to improve the opportunities for young adults to generate income and strengthen their resilience in everyday life. Increasing well-being throughpsychosocial services in the context of violence, flight and lack of prospects. 3 international LZFK, 9 national LZFK, as well as 500,000 EUR financing and 829,500 EUR material assets are used. |
| Key outputs | (1) The capacities of smallholder households are strengthened with regard to agricultural production and food. (2) The range of needs-based, gender, context- and conflict-sensitive qualification measures for the target group has been improved. (3) Local state and non-state actors have improved capacity to provide low-threshold psychosocial support to the target group. |
| Cooperation | None |
| Order | 5,850,000 euros |
| Runtime | From 10/2021 to 12/2024 (3 years and 3 months) |

# 2.	Classification of the project

## 2.1	Classification of the module in the strategic reference framework

The project is not part of an development cooperation programme, but an individual measure within the special initiative "Tackling the root causes of displacement – reintegrating refugees" (SI Flucht), to whose field of action 2 (stabilisation of host regions and integration of refugees and internally displaced persons in the host regions) it contributes. With regard to the "BMZ 2030" reform concept, the project is assigned to Action Area 3 (Displacement and Migration) of Core Topic 1 (Peace and Social Cohesion). In addition, it makes  a significant contribution to core themes 2 (A world without hunger) and 3 (training and sustainable growth for good jobs) through food security and employment promotion measures. There is currently no country strategy for South Sudan, and bilateral negotiations are not taking place.

The project is in line with the BMZ strategy paper "Agriculture, Rural and Territorial Development" and the "Berlin Charter" for creating opportunities for the young generation in rural areas. It complies with the relevant development policy requirements of the BMZ. These include, in particular, the BMZ sector concept "Development for Peace and Security" (04/2013), "Human Rights in German Development Policy" (04/2011), sector-specific topics such as "Private sector promotion" (09/2013), "Vocational education and training in development cooperation" (11/2012) and BMZ's development policy "Action Plan for Gender Equality 2016-2020" (03/2016).

In addition, the project ties in with the Federal Government's interdepartmental guidelines "For a coherent policy of the Federal Government towards fragile states" (2012) and "Preventing crises, resolving conflicts, promoting peace" (2018). It is also committed to the principles of Leave no one behind (LNOB) and Do-no-harm and will pay particular attention to the specific needs of women, young adults, people with disabilities and members of other disadvantaged groups.

As part of the Federal Government's "Strategy for Migration and Development – Action Plan for the External Dimension of Migration and Refugee Policy" (2016), the project aims to "improve protection and support for refugees in the main host countries", which aims to improve the protection and support of refugees in the main host countries., IDPs) and host communities. The project contributes to the implementation of the Global Action Plan to Improve the Situation of IDPs (2018) by strengthening the economic participation of IDPs and returnees and the communities that host them. The Global Compact on Refugees (GCR), which forms the overarching international political framework on displacement, includes important principles such as strengthening the self-reliance of refugees and the important role of host communities. These principles are also relevant in dealing with internal displacement and return.

## 2.2	Other development measures in the specific area of intervention of the module

German development cooperation in South Sudan is currently working on three priority areas: food security, good governance, and water and sanitation. The planned ÜH project "Food Security and Natural Resource Management (Complementary Project to WFP/Unicef)" (PN 2021.1853.7; LZ: 10/2021-06/2025), the planned bilateral agricultural project (cooperation with IFAD, PN: 2021.2107.7, LZ: tbc) and the TC project have a complementary effect in strengthening agricultural production and food security (outcome level). There is potential for synergies with the FC in the area of strengthening agricultural production (outcome level), esp. with the KfW project "Reconstruction and strengthening of basic income support for internally displaced persons and returning refugees, South Sudan" (BMZ No. 2019.40.592, SI Flight). Furthermore, the FC project "Strengthening resilience in urban areas" (BMZ No. 2019.18.671, transitional assistance) is relevant, especially in the areas of food security, health and education. Through the use of synergies (further development and improvement of concepts and technical approaches, additions within the selected intervention zones), a significant reduction in costs for the German development cooperation system can be expected (economic efficiency).

Welthungerhilfe (WHH) is currently involved in the development of South Sudan with 19 projects. With WHH, there is a high synergy potential by supporting smallholder families in their new start in agriculture at the outcome level. Essential contents are soil-conserving and gentle methods of agriculture and the introduction of drought-resistant plants. In doing so, WHH strengthens agricultural cooperatives and supports Village Savings and Loan Associations (VSLA) in the states of Eastern and Central Equatoria.

The intervention zone for the South Sudan Livelihoods and Resilience Programme (SSLRP) of the International Fund for Agricultural Development (IFAD) is identical to the states of Eastern and Central Equatoria, at least on a large-scale scale, so that interaction in terms of networking and exchange is a lesson learnt of the addressed cooperatives and that this will result in added value (output level).

The EU supports a green and resilient economy through the Multi-annual Indicative Program (MIP) (2021-2027) and its Human development, jobs and growth for a resilient stable society initiative  . The final portfolio is still in the coordination or development phase. Discussions during the audit mission revealed a high potential for synergy and possible cooperation in the areas of economic diversification, jobs for young adults, human development, and education and health. (Impact level)

| Donor | Intend | Expected synergies at the impact levels |
| --- | --- | --- |
| BMZ | "Complementary projects (to WFP/UNICEF) on food security and natural resource management" (TC) "Reconstruction and strengthening of basic income support for internally displaced persons and returning refugees, South Sudan" (FZ); "Strengthening Resilience in Urban Areas" (FZ) "Back Home – A New Start in Agriculture" (Welthungerhilfe) (in: Equatoria State (EES) and Central Equatoria State (CES)) | Strengthening agricultural production and food security (outcome level) |
| IFAD | "South Sudan Livelihoods and Resilience Programme (SSLRP)" (in: EES (Magwi and Torit); CES (KajoKeji and Terekeka)) | Implementation of development plans of cooperatives/farmer groups with the participation of local structures to cover the short-term needs of farmers (outcome level) |
| EU | "Human development, jobs and growth for a resilient stable society" | Green and resilient economy: food security, jobs for young people, economic diversification, climate change and human development: education and health. Final portfolio is still in the coordination or development phase (impact level) |
| IOM / IMC | Projects in the field of MHPSS | Provision of psycho-social support and psychological treatment in the context of flight and violence; Development of national strategies/policies as well as pleas in the area of MHPSS (impact level) |

# 3.	Problem and potential analysis (related to the TC module)

Initial situation in the area of intervention: South Sudan is the fourth most fragile country in the world (Fragile States Index, 2021), after Yemen, Somalia and Syria. Since South Sudan's independence in 2011, armed conflicts and ongoing crises have contributed to a steady deterioration in food security, in particular. Currently, 7.6 million people are considered food insecure, including 1.9 million women and children. Following the escalation of violence in 2013 and 2016, 2.2 million people have fled South Sudan to neighbouring countries (more than 80% of them women and children), and 1.6 million are internally displaced. Child and forced marriages are on the rise, with just under a quarter of female IDPs saying they have experienced SGBV (Sexual and Gender Based Violence ). Young men are struggling with the fact that they can no longer fulfil their role as providers in the context of expulsion, as provided for in the classic role model. In addition, there are other obstacles to development such as inadequate access to education (more than 60% of people over the age of 15 are illiterate, compared to over 70% for women and girls), high unemployment (estimates put the figure at up to 50% of youth unemployment) and the associated impoverishment of young people. Traditional land rights structures dominate, especially in rural areas. Corruption is widespread, especially in areas with a high influx of returnees (former refugees and internally displaced persons), conflicts over ownership and access to land are very common.

The "National Framework for Return, Reintegration and Relocation of Displaced Persons" (2017) prioritises not only the security of returnees, but above all the stabilisation and diversification of livelihoods as well as access to food and education. The "South Sudan Durable Solutions Strategy and Plan of Action" is currently in progress. Finally, a draft of a South Sudanese national MHPSS strategy is currently being developed. As one of the five goals of South Sudan's National Development Strategy (NDS) 2018-2021, the focus is on creating jobs and improving living conditions. The South Sudanese agricultural concept (Comprehensive Agricultural Master Plan, CAMP) provides the strategic orientation for the development of the agricultural sector until 2040. The Cooperative Law of 2011, the National Cooperative Development Policy 2013-17 and the National Strategy for the Development of Cooperatives (NSCD) 2012-15 provide the framework for the development of the cooperative movement.

The National Gender Policy Strategic Implementation Framework (2012); the Guidelines on Women and Child Rights for the South Sudan National Police Personnel (2015) and the South Sudan National Women Strategy  (2016), regulate the rights of women, young adults and children in South Sudan at national level. The Interim Constitution of South Sudan of 2011 stipulates that all levels of government must "promote the sustainable management and use of natural resources [...] ".

Derivation of the module goal: Due to the poor economic situation and the still very tense security situation, the local population as well as the returnees and internally displaced persons lack access to resources, income prospects and basic services. At the same time, children and young adults, and especially girls and women, have insufficient access to basic education, qualification and training. Overall, both host and returning populations and internally displaced persons are often unable to make a living and thus secure their food, and their psychosocial burdens are very high due to the ongoing experiences of violence and displacement (core problem).

The measure focuses on strengthening the resilience of the target group through an improved integrated agricultural production system, combined with qualification measures for women and young adults. The project also includes psychosocial support measures.

The aim of the module is to improve the nutritional, economic and psychosocial living conditions of returnees, internally displaced persons and members of host communities.

Causes and assessment of changeability: The central cause of the current food insecurity is the ongoing civil war. This cause cannot be changed by the project. In large parts of the country, agricultural production has collapsed and/or fallen even further from an already very low starting level. This applies in particular to the people in the high-yield Equatoria states, who are no longer able to take up or expand cultivation on their own. The associated crop failures increase food insecurity. The agro-economic cycles are disrupted and the movement of goods, people and services is severely restricted. These causes can be changed by the project by offering appropriate seeds and inputs, setting up cooperatives and strengthening the capacities of the rural population in the area of production and nutrition. The capacities of (non-)state actors in the field of psychosocial support are very weak. In addition, stigmata reduce access to the few MHPSS services. These causes can be changed by the module by improving the offers for the target group by strengthening the capacities of state and non-state actors and focusing on reducing stigmas.

Results achieved so far: The present proposal builds on the experience of the bilateral project "Food Security and Agricultural Development" (PN 2017.2059.8), in which smallholder farmers, who often achieve low agricultural yields and operate inefficiently, are trained in the economic and agricultural basics. The food security of over 8,000 children and over 4,600 women has been improved. In addition, more than 18,000 households have resumed or expanded agricultural production. In Magwi, teachers from the local agricultural institute have already been able to take part in further training courses on the approach of the Farmer Business Schools (FBS)  as a result of this project.

# 4.	Objectives, impact hypotheses, indicators and partners of the TC module

## 4.1	Objectives, target groups, impact hypotheses and indicators

Module objective: The nutritional, economic and psychosocial living conditions of returnees, internally displaced persons and members of host communities are improved.

| Indicators | Underlying | Target |
| --- | --- | --- |
| Module target indicator 1: The average value of food groups consumed according to IDDS-W (Individual Dietary Diversity Score for Women) of 1,000 women (of which 50% from households of host communities, 20% from households of internally displaced persons, 30% from households of returnees) has increased by 0.5 food groups. | 2.5 food groups | 3.0 Food groups (12/2022: 2.6; 12/2023: 2.8; 12/2024: 3.0) |
| Module target indicator 2: 195 of the 300 participants in gender-, context- and conflict-sensitive training measures, of which 50% are members of host communities, 20% are internally displaced persons and 30% are returnees, 60% of whom are women and young adults, confirm that their income prospects have improved. | 0 out of 300 participants (no corresponding survey has been conducted so far) | 195 of 300 participants (12/2024) |
| Module target indicator 3: 150 out of 200 people who have taken advantage of low-threshold psychosocial support services (of which 50% are members of host communities, 20% are internally displaced persons and 30% are returnees, 60% of whom are women) use a concrete example to confirm how gender, context- and conflict-sensitive psychosocial support has increased their psychosocial well-being. | 0 (Offers are aimed at people who have not previously been provided with offers) | 150 Persons (12/2024) |

The baseline and target values of indicators 1, 2 and 3 are provisional. They will be reviewed in the first year of implementation and adjusted if necessary as part of the initial reporting. For further details, see the graphical representation of the impact logic and the impact matrix in the appendix.

No national SDG indicator was used. South Sudan does not yet have a national 2030 Agenda. The process of developing a national 2030 Agenda was launched in 2015 by a national dialogue conference. Due to political unrest and the change of government in 2020, the process stalled.

The project refers to the following SDGs of the international 2030 Agenda: SDG 1 (zero poverty), SDG 2 (zero hunger), SDG 4 (quality education), SDG 16 (peace, justice and strong institutions) and SDG 5 (gender equality).

Target groups: The target group is returnees, internally displaced persons and vulnerable members of host communities in the counties of Magwi, Torit and Ikotos in the state of Eastern Equatoria and the counties of Yei and Morobo in the state of Central Equatoria in South Sudan. According to UN information, the spontaneous flows of returnees are currently concentrated in the states of Eastern and Central Equatoria, Unity, Jonglei and Upper Nile. According to the latest data collected by the IOM, as of December 2020, there were 247,115 IDPs and 178,822 returnees in the state of Central Equatoria. In Eastern Equatoria, there were 88,103 IDPs and 157,010 returnees. Compared to the previous survey from September 2020, this means an increase in IDPs and returnees in the two states as a whole as well as in the five selected counties. In the district of Magwi, the number of IPDs has almost quadrupled within six months from 13,724 to 40,684 individuals. With 92,444 individuals, Magwi is also one of the districts with the largest increase in returnees. In Torit and Ikotos, the number of returnees as well as IDPs has also increased. Yei is among the counties with the highest total number of IDPs with 52,415. The number of IDPs in Morobo has increased fivefold from 2,740 to 13,094.

According to data from IOM and OCHA, 201,619 women, 185,640 men and 449,826 children live in the five project counties. The average household size is about 7 people, with children making up over 50% of the household members and adult men and women each just under a quarter. 73% of households are considered to be women-headed. Almost half of all households have at least one person with a physical or mental impairment.

The returnees come from neighbouring countries as well as from other federal states and districts. In some cases, they do not return to their original villages, and in many cases they are only parts of the household. Poor and vulnerable people make up the majority of the target group. The project involves the host municipalities in all measures in line with the integrative approach and follows the do-no-harm approach. The special needs of people with disabilities are also taken into account.

The project is facilitated by representatives of local communities, NGO staff, teachers and trainers from vocational training institutions and staff from local health stations, as well as representatives of women's organisations and farmers' associations, and representatives from the private sector.

Impact hypotheses: It is assumed that improved subsistence farming and the marketing of products can contribute to securing livelihoods and thus food security for the population groups mentioned. In addition to the provision of inputs and agricultural equipment, education and skills measures geared towards everyday life and employment are intended to improve the opportunities for young adults to generate income, strengthen their everyday resilience and potentially find employment in the agricultural sector. Psychosocial services improve the well-being of the population in the context of violence, flight and lack of prospects.

Output 1 focuses on strengthening the capacities of smallholder households of internally displaced persons, returnees and members of host communities in terms of agricultural production and nutrition. By advising on the improvement of production methods, the provision of seeds and planting material (main cereals, legumes, fruit and vegetable seeds) and inputs in conjunction with nutritional advice, the project contributes to securing and diversifying nutrition. The effect hypothesis is that improved subsistence farming and marketing of the products contribute to securing livelihoods and thus, in conjunction with nutritional advice, to food security for the above-mentioned population groups (module goal). This is done on the assumption that the effects of extreme weather events and the prevailing security situation do not significantly affect agricultural activities and harvests.

Output 2 aims to improve the range of needs-based, gender-, context- and conflict-sensitive qualification measures in the field of agriculture and entrepreneurship, including functional literacy and basic arithmetic.

The effect hypothesis is that (1) beneficiaries will be qualified through methodological and technical advice for the development of needs-based offers for gender-, context- and conflict-sensitive qualification measures, (2) through the procurement of modern equipment for the two vocational school centres to be funded in accordance with the requirements of the newly introduced offers, and (3) through the further training of teachers and trainers at these centres,  who have improved income prospects with their professional and social skills (module goal). This is done on the assumption that the vocational school centres and their teachers are mandated and prepared to implement the offers for the target group quickly and systematically.

Output 3 aims to strengthen the capacity of state and non-state actors to provide psychosocial support services to internally displaced persons, returnees and members of host communities. The hypothesis here is that the target group increases their psychosocial well-being by using the offers (module goal). At the same time, the anchoring of the psychosocial approach as a cross-cutting topic in the implementation of all outputs contributes to increasing the effectiveness of all measures (module target level). This is done on the assumption that the psychosocial services are both designed and implemented in a needs-oriented manner and taken up by the target group.

The BMZ's strategic guidelines were taken into account.

## 4.2	Sponsors and partner structure

Political executing agency: The implementation of the project is carried out in accordance with the BMZ, applying Section 47 of the FZ-TC Guidelines, in principle independent of the government. Official government negotiations with the government in South Sudan remain suspended even after the formation of a new unity government (February 2020). In response to the outbreak of civil war in December 2013, German development cooperation in South Sudan was redirected. The focus of its commitment is on supporting particularly vulnerable target groups outside the government, including through cooperation with non-governmental organisations and international organisations. Within this context, the TC project has no political sponsor.

The institutions of the downstream partner structure are, at regional level, the Ministries of Agriculture of the States of Eastern and Central Equatoria (State Ministry of Agriculture), and in particular the competent county administrations in both states, such as the Directorate of Agriculture, the Directorate of Cooperatives and Rural Development, (Directorate of Cooperatives and Rural Development) and the Directorate of Forestry.

Implementation partners for the work in the entire spectrum of the target group are cooperatives and farmers' groups. In Central Equatoria, 10 cooperatives are registered with a focus on crop production and another with a focus on processing (as of October 2020). In Eastern Equatoria, 6 cooperatives are active in crop production and another in agro-processing . The majority of cooperatives face similar challenges, such as weak financial resources, poor management skills and inadequate or poorly organised services for members.

Both the training centre in Yei and the Magwi School of Agribusiness have a high degree of operationality and stability compared to other qualification institutions in South Sudan. Both centres are currently offering a range of short-term training courses in the agricultural sector. The training centre in Yei is subordinate to the MAFS, but has a high degree of autonomy.

The decision-makers in the administration at district and municipal level as well as traditional authorities of the state agricultural extension services, vocational training centres, as well as local health care structures are important implementation partners and mediators of the project. Psychological or psychiatric treatment does not usually take place, there is only one psychiatric clinic in the entire country and only a few psychologists or psychiatrists practicing in the public sector. A referral of patients with mental illnesses is therefore not very promising in the state system. A takeover by actors from the UN or international NGOs seems more likely.

# 5.	Design of the TC module

## 5.1	Methodological approach and duration

Duration: From 10/2021 to 12/2024 (3 years and 3 months)

Strategy: As part of the special initiative "Tackling the root causes of displacement - reintegrating refugees", the project contributes to field of action 2 (stabilisation of host regions and integration of refugees and internally displaced persons in the host regions)". The special initiative is designed to reduce the causes of displacement and mitigate negative effects. The focus is on improving people's livelihoods and conditions, reducing poverty and contributing to improved food security. The measure pursues an integrative approach in which internally displaced persons, returnees and vulnerable members of the host communities are jointly supported. The project follows the do-no-harm approach and establishes a conflict-sensitive monitoring system so that unintended negative effects are identified, avoided and reduced at an early stage.

Overall, the local planning and implementation skills of the partner structures are very weak. Therefore, their qualification is an essential part of the project. The relevant technical services on site will be enabled to actively accompany parts of the project. Civil society organisations are also strengthened in their self-help capacities and involved in project implementation. In line with BMZ's requirements for non-governmental implementation , the TC project focuses on the meso (regional administrations) and micro levels (municipalities and households) and involves various actors from local administrative structures, civil society and the private sector (multi-actor approach). The objectives for the project can be achieved within the specified period.

The project follows the eligibility criteria defined by BMZ for the design of measures in a fragile environment (establishment of an adequate security risk management system and setting up a context-sensitive impact monitoring system).

The fact that the new project can build on extensive learning experiences, tested instruments, methods and approaches, as well as existing infrastructure and trained personnel, which have been built up and trained in the ongoing food security project FSAD, has a positive effect on the implementation of the project. In output 1, for example, these are: the partly already established cooperatives as well as trainers and training formats for the FBS approach. In Output 2, the project is cooperating with already established training centres in order to be able to start expanding the range of services directly. In Output 3, the project is already in contact with IOM and IMC, the co-chairs of the MHPSS working group in South Sudan.

Use of instruments: 4 international and 6 national long-term experts, KZE, material assets worth EUR 829,500 and financing worth EUR 400,000 will be used for the implementation of the project.

An international LZFK takes over the responsibility for the order and the country directorate (Output 1-3). Another international LZFK supports the content and budget management and ensures the anchoring of the cross-cutting topics of "mental health and psychosocial support" as well as "gender, conflict and trauma sensitivity" in all project fields (output 1-3). Two other international LZFK (proportionately) support the AV in financial management and in monitoring and evaluation (output 1-3). Due to the remote control, a national LZFK takes over the coordination of the project activities on site (Output 1-3). Five national LZFKs are responsible for the implementation of the 3 outputs supported by KZE.

The targets for development workers and integrated experts for South Sudan remain set at 0 due to the fragile security situation.

Parts of the project, esp. in Output 1 and 3, are implemented through financing contracts with international NGOs. Among other things, a cooperation with Caritas SwiTCerland in the state of Eastern Equatoria is planned.

Output 1 aims to strengthen the capacities of smallholder households with regard to agricultural production and food. This includes increasing food security through diversified food production and providing nutritional advice to internally displaced persons, returnees and host communities. To this end, additional food groups such as vegetables, legumes, fruits, animal products from small animal husbandry (e.g. milk/meat/eggs) are integrated into the production. The increase and diversification are intended to benefit women and children in vulnerable smallholder households in particular, but at the same time create opportunities to farm and generate income even on small areas (kitchen gardens). Finally, the project conducts training courses on healthy nutrition for mothers and other family and community members (e.g. husbands, village heads).

Based on the guiding principles of locally adapted agricultural use, farmer groups are supported throughout the entire production process on the basis of the Farmer Business Schools (FBS) approach introduced in GIZ's predecessor projects. In the FBS approach, farmers learn how to jointly try out and reflect on innovations in their own fields and gardens as well as aspects of economic activity.

As a supporting structure, the measure supports established agricultural cooperatives and promotes the merger of other smallholder households into organised production associations. In such organisations, returnees and internally displaced persons can be integrated and organised, which creates production opportunities for this part of the population and can reduce conflicts with host communities. It also facilitates access to finance and provides opportunities for advocacy.

The selection of participants for the training courses is conflict- and gender-sensitive, with special consideration given to representatives of women-led households. When using digital solutions, care is taken not to exclude particularly vulnerable target groups in the sense of the "Leave no one behind" (LNOB) approach.

Milestones: Seed distribution completed; Completed FBS training on improved farming methods; Completed training on healthy eating.

Output 2 aims to expand the range of needs-based, gender-, context- and conflict-sensitive qualification measures for returnees, internally displaced persons and members of host communities, especially women and young adults, in the agricultural sector (closely linked to Output 1). This is achieved through targeted cooperation with training centres with a focus on the agricultural sector. The need for qualifications is examined with local associations and compared with labour market analyses by other actors and existing qualification offers. The specialists and managers of the training centres in Yei and Magwi are being trained to expand their range of training courses in terms of both quantity and quality. In addition, they are trained to integrate non-violent conflict management into the various courses and to link them with the activities of active psychosocial support (see Output 3). As a prerequisite for a self-determined life, specific courses on literacy and catch-up basic training are offered. In addition, basic financial education offers are implemented to support budget planning or trade. Finally, in order to promote entrepreneurship (especially agricultural), courses and mentoring programmes for young entrepreneurs are planned, including strengthening savings groups and generally improving access to financial services.

The output is aimed at opening up perspectives and employment opportunities. This is a relevant contribution to local peacebuilding and lays the starting point for structure-building, long-term development measures in the sense of the Linking Relief, Rehabilitation and Development (LRRD) approach. In view of the Corona pandemic, the use of digital methods must also be examined.

Milestones: Qualification requirements have been determined; Training courses for specialists and managers of the training centres have begun; needs-based offers have been developed and incorporated into the concepts and offers of the training centres

Output 3 aims to strengthen the capacities of state and non-state actors to provide psychosocial services to internally displaced persons, returnees and vulnerable members of host communities. The aim is to enable them to support the target group in developing positive coping strategies in dealing with experiences of violence and displacement as well as a lack of prospects. The measures are flanked by capacity development and qualification approaches in Output 1 and 2, starting on the one hand with the governmental and non-governmental implementation partners of the measures of Output 1 and 2 (e.g. agricultural and nutrition consultants, teachers of the training centres), on the other hand with staff of local health centres (midwives, nurses), specialised local NGOs and representatives of the communities (e.g. traditional healers, women and men with a role model function). The focus is on the development of skills at the level of the people through further training and advice, but the organisations are also strengthened, e.g. by integrating the topic into their processes. Through their networking with relevant actors in the field of MHPSS at the national level (e.g. international NGOs and organizations of the UN system), the level of society is also strengthened to a lesser extent.

The psychosocial support services aligned with the MHPSS Orientation Framework include, for example: accompanied self-help and support groups, reflection rounds, sporting and cultural events, coaching and mentoring by trusted persons. At the same time, awareness-raising measures are also aimed at reducing psychosocial stigmas.

In addition to the specific, low-threshold support services, the psychosocial approach is integrated as a cross-cutting topic in the conception and implementation of agricultural, educational and nutritional measures. Another part of the capacity building is further training and counselling on the topic of referrals, i.e. the skills to recognise mental illnesses that require medical treatment by psychologists or psychiatrists, as well as to train them further.

Finally, the implementation of joint activities for internally displaced persons, returnees and host populations can promote the establishment of constructive relationships between the different groups and the reduction of prejudices (e.g. mixed groups in nutrition counselling; taking into account different cultural customs and methods of preparation, if any; common consumption, etc.).

Milestones: First cohort of implementation partners trained in the psychosocial approach, first specific psychosocial services provided (e.g. self-help groups, cultural and sporting events).

| Outputs* | Main activities | Timeframes/milestones | Instruments used (number / order of magnitude) |
| --- | --- | --- | --- |
| Output 1 | Provision of high-quality seeds and planting material & inputs Consulting and training of smallholder cooperatives (access to land, increase production, marketing and financial management) Nutritional counseling for mothers and other family and community members | Seed distribution completed (12/2022) Training courses on improved cultivation techniques carried out (12/2023) Training courses on healthy nutrition completed (12/2023) |  |
| Output 2 | (Continue)Development and implementation of qualification measures in the field of agriculture and entrepreneurship (Re-)Establishment of educational centres Expert advice for micro-enterprises, e.g. Further training on entrepreneurial action, financial resources and mentoring programmes, including advice on financing, e.g. to VSLAs Carrying out whereabouts examinations (tracing) | Qualification needs have been identified (03/2022) Training courses for specialists and managers at the training centres have started (05/2022) Needs-based offers have been developed and incorporated into the concepts/offers of the training centres (10/2022) |  |
| Output 3 | Educate implementation partners of outputs 1 and 2 on the psychosocial approach Training core staff and local community liaisers in psychosocial support Specific psychosocial services (e.g. self-help groups) Awareness-raising measures to reduce stigma Advice on referral to specialized medical institutions | First cohort of implementation partners trained in psychosocial approach (end of 2022) Initial specific psychosocial services provided; e.g. Support groups, cultural and sporting events (end of 2022) |  |

## 5.2	Ensuring the sustainable effectiveness of the measures (outcomes)

The project's structure-building approach aims to ensure long-term effects. Increasing agricultural production and productivity as well as nutritional advice help the target group to improve their livelihoods, esp. with a view to food security. Technically and organisationally strengthened cooperatives and other associations form the structural basis for a sustainable increase in production that is not dependent on external inputs, as well as the integration of returnees and internally displaced persons (exit strategy).

The offers for qualification in agriculture, crafts and small businesses open up further income opportunities for young adults in the medium and long term. By providing means of production in conjunction with qualifying measures that go beyond traditional subsistence farming (e.g. Farming as a Business training for farmer groups, qualification courses for young adults and women), the self-help capacities of the target groups are strengthened so that they can continue some of the activities independently in the future (exit strategy).

The increased capacity of state and non-state local actors in the field of MHPSS creates an initial basis for anchoring the topic at the institutional level, especially in the form of trained staff and community representatives. The former can use their competencies in the field of MHPSS in their work in the long term on the condition that their structures continue to exist and are functional. Local community members are expected to be able to contribute within their communities even after the end of the project and without additional funding. In addition, the target group of psychosocial support measures benefits in the long term by using the newly acquired coping strategies at the individual and community level. The use of participatory approaches allows for the involvement of all stakeholders.

## 5.3	Partner services, combined financing

|  | Concretization | Estimating the value |
| --- | --- | --- |
| Combined financing | - | - |
| Partner services | Partner services consist of the provision of staff from the Department of Agriculture at the local level and staff from local administrations at the state and municipal level. Furthermore, the schools and the cooperatives provide appropriate staff and premises. |  |

## 5.4	Order value and detailed cost estimate

Contract value:

The contract value also includes costs for participation in the Sector Network for Rural Development (SNRD) in the Network International Cooperation in Conflicts and Disasters (NICD) and the Network for Economic Development in Africa, (NEDA) with the aim of ensuring the technical quality and knowledge management required for the implementation of the contract. The contract value also includes the costs for an evaluation (interim/final evaluation) of the project as an essential instrument for monitoring the success and accountability of the German TC.

The preparation of the project is also part of the contract. The upfront costs of the measure will be transferred to the project after commissioning or, if not commissioned, to the Study and Skilled Workers Fund (PN: 19.4063.4).

For a detailed overview of costs, please refer to Appendices 3a "Cost estimation and outflow of funds by financial year" and 3b "Cost-output allocation".

# 6.	Assessment of the effects and risks of the module

## 6.1	Impact assessment

General results: The measure contributes to the international development goals of the 2030 Agenda, in particular SDG 1 (No Poverty), SDG 2 (No Hunger), SDG 4 (Quality Education), SDG 16 (Peace, Justice and Strong Institutions) and SDG 5 (Gender Equality).

The proposed measure focuses on improving the living conditions of internally displaced persons, returnees and vulnerable members of host communities. In particular, the resilience of individuals, smallholder households/farms and the communities in which they are embedded is strengthened. The economic and financial impact will be achieved through strengthened and diversified livelihood strategies, improved access to credit, savings and productive assets, greater connection of producers to markets, and greater financial sustainability of key market actors. The technical implications are the adoption of new practices and technological innovations that significantly increase the resilience of individuals, households, and communities. These measures and the focus on agricultural cooperatives, farmer groups and member farms are intended to improve food security. The project thus consistently follows the implementation principle of an integrated approach at the level of general effects. The project has a peace-building effect by carrying out joint activities for internally displaced persons, returnees and the host population in a way that strengthens social relationships and through psychosocial support (SDG 16). By focusing on internally displaced persons, returnees and the vulnerable local population, the project reduces the disadvantage of particularly vulnerable people and thus implements the principle of "leave no one behind".

Economic effects: In order to strengthen smallholder producers, the measure supports agricultural cooperatives in the intervention zone and the association of smallholder households into organised production associations. In conjunction with training on improved cultivation methods and economic action, better purchase prices for the purchase of agricultural means of production are to be negotiated and higher prices for the sale of the harvest are to be achieved. These increases in agricultural production and productivity help the target group to secure their economic livelihoods and thus their food independently. It is to be expected that the bundle of measures will also be accompanied by an improvement in resource efficiency. Furthermore, the offers for qualification in agriculture, crafts and small businesses open up further income opportunities for women and young adults in the medium and long term. By creating new and integrative concepts, the field of action dovetails the practical training of women and young adults with the opening up of perspectives and employment opportunities. Internally displaced persons, returnees and the vulnerable host population are finally integrated into the social life of the community through the provision of psychosocial support and can thus participate in working life and economic processes again.

Ecological impacts: The guiding principle of the project is locally adapted agriculture. To this end, the project conducts training courses on improved cultivation techniques (soil fertility, sowing techniques, sustainable field and garden maintenance, harvesting techniques, etc.) for local smallholder households. The guiding principle excludes the use or financing of chemical pesticides. This is done both from an ecological point of view and with a view to the low purchasing power of small farmers. Potential conflicting goals between the ecological and economic dimensions are minimized by the approach of increased production in the form of largely organic horticulture and agriculture (use of organic fertilizers,  seeds adapted to climatic conditions). The other fields of action of the project have no or very little influence on the dimension of ecology.

Social impact: The project pursues an integrative approach. Internally displaced persons, returnees and vulnerable members of host communities together form the target group. Positive interactions between the social and economic dimensions are an integral part of the project's overall approach, e.g. in the development of cooperatives. With this approach, constructive exchange relationships between the groups are promoted, so that tensions can be defused or constructively overcome. The measure aims to a) build resilience (empowerment, future planning, self-efficacy) at the individual and community level and b) strengthen social cohesion (through inclusive, self-motivated collaborative planning and execution of work). Since this applies in principle to all population groups, the principle of "leave no one behind" is taken into account. The project contributes to improving gender relations by addressing the causes of inequality (e.g. access to land, finance or education/skills for women and young adults). This will lead to a lasting change in the decision-making possibilities of women and young adults about their own lives.

Conclusions for the design of the module: The three outputs of the project are intertwined, so that positive interactions arise (see chapter 4.1). Based on overarching gender, human rights and conflict analyses, the outputs are implemented in a context-, conflict- and gender-sensitive manner so that unintended negative effects are avoided and potentials for peaceful and gender-equitable development are promoted.

Identifiers, markers and cross-cutting topics are summarised in table form in Appendix 4.

## 6.2	Assessment of the risks to the effectiveness of the module

Political risk: Due to the ongoing political and economic instability as well as the fragile security situation, the framework conditions in South Sudan will remain uncertain and volatile for the foreseeable future. Violent conflicts can break out (again) at any time in various areas of the country, but the risk of a new civil war is currently estimated to be low. Without peace and currency reforms, the economy will continue to deteriorate in the coming years, which can lead to further depreciation of the currency, hyperinflation of prices and, as a result, an increase in insecurity and crime. The political risk is classified as high, the ability to be influenced by the project as low.

Implementation risks:  Displacement, security risks for the population in rural areas, looting and difficult access to markets can continue to discourage smallholder households from cultivating their fields and generating income. Conflicts between farmers and livestock breeders over the use of the land can also affect project activities. There is a generally high incidence of violent crime (violent robberies, burglaries, kidnappings). The risk of default is high. Equipment as well as facilities and material of any kind can be damaged, destroyed or stolen or inaccessible due to conflict and war events or vandalism and looting. The complete loss of stocks at individual locations includes the loss of sites and intervention sites, not least in the event of air traffic being affected by war or infrastructure failure. A suspension of the implementation may be necessary due to the security situation, e.g. by obstructing or assaulting implementation personnel. If the COVID-19 pandemic situation persists, negative effects on the profitability of the measure must also be expected, including a reduction in the transport of goods (due to border closures) or the negative effects of lockdown measures.

Security risk management and personnel security requires the provision of adequate resources, which leads to higher implementation costs overall. The implementation risk is classified as high, the ability to be influenced by the project as medium.

Long-term anchoring risk: The risks to long-term anchoring consist of a lack of long-term stability and operationality of partner groupings at the target group level. Financial losses for smallholder farmers, staff turnover at governmental and non-governmental partners, and climate-related risks such as floods and droughts represent the highest and most likely risks. The risk for long-term anchoring is classified as medium, and the ability to be influenced by the project as medium.

Environmental and social impact of the measure: Potential conflicting goals between the ecological and economic dimensions are minimised by the approach of largely organic gardening and agriculture (use of organic fertiliser, seeds adapted to climatic conditions). Increased land consumption is counteracted by predominantly small couple cells (such as kitchen gardens).

The social risk of not sufficiently addressing the host municipalities is prevented by the specifications in the project indicators and the integration of the municipalities in the planning and implementation of the measures. The intensification of conflicts between interest and user groups, ethnicities or gender groups is counteracted by the active and transparent participation of the entire social spectrum. This also applies to taking into account the needs of women and young adults as well as other vulnerable groups (older people, people with disabilities, ethnic minorities). There is a risk that in the case of unprofessionally provided psychosocial support by implementation partners, existing stress and trauma will be exacerbated or retraumatisation will occur. This risk can be reduced by providing close and high-quality technical support through the project. The risk of the measure having a negative impact on the environment and social issues is classified as medium, and the ability to be influenced by the project as medium.

Corruption risks: As corruption is widespread in the partner country, there is a risk that new cases or allegations of corruption among partners of the project will lead to a loss of credibility and trust on the part of other actors and/or citizens, and ultimately affect certain integrity promotion initiatives or dialogue mechanisms. The project aims at the broad participation of different actors in reform processes and exchange platforms, so that central decisions cannot be influenced by the particular interests of a few participants.

Within the framework of the project, the risk of corruption can be reduced through consistent compliance with internal procurement and contract processes, sufficient financial and procurement personnel and close accounting support for partners (esp. beneficiaries). Established partners are used for financing. A close-knit network of monitoring measures will be established for the provision of inputs (e.g. seeds, small animals and equipment). The risk is assessed as high, the ability to be influenced is assessed as medium.

Overall risk: The overall risk is rated high, the ability to be influenced by the project as medium.

| Risk | Classification* | Influenceability* | Risk management measure |
| --- | --- | --- | --- |
| Political risks |  |  |  |
| Intensification of the armed conflict, deterioration of the security situation Political instability and further weakening of the state | 3 | 1 | Flexible project approach, rapid response to change, regular risk assessments and analyses; timely provision of support to relevant actors at local/regional level; Creation of spaces for peaceful dialogue and confidence-building |
| Implementation risks |  |  |  |
| Food security deteriorates and affects the ability of beneficiaries to participate in project activities The influx of internally displaced persons into the destination areas leads to increased demand for products and a decline in agricultural production Conflicts between farmers and ranchers affect project activity Potentially high security risks for national personnel and partners Generally high level of violent crime (violent robberies, burglaries) Risk of psychological stress and high stress Natural disasters (droughts, floods) Ongoing COVID-19 pandemic situation | 3 | 2 | Flexible planning approaches, active participation in the coordination mechanisms of local authorities and the international community Regular update of context and stakeholder analyses Working closely with OCHA and other partners to monitor population movements within the target areas Conducting regular market assessments and monitoring food prices to be able to adapt to fluctuating demand Conflict resolution training with the involvement of pastoralists who specifically address typical triggers for conflict Small-scale agricultural activities (e.g. vegetable cultivation, kitchen gardens) to keep the potential for conflict low Strong GIZ security risk management, including the provision of adequate resources |
| Risk for long-term anchoring |  |  |  |
| Lack of adaptation of innovations, staff turnover at institutions, financial slumps at institutions and groups | 2 | 2 | Comprehensive strengthening of cooperatives/farmer groups, vocational schools and health care structures in the area of MHPPS, orientation of measures to a high rate of adaptation |
| Environmental and social impact of the measure (unintended effects) |  |  |  |
| Inefficient use of available local resources (overuse) Use of environmentally harmful products in agriculture (synthetic fertilizers, pesticides) Increased land consumption Increasing conflicts between interest and user groups, ethnicities, gender groups, etc. by not including them in project activities Exacerbation of stress and trauma due to unprofessional psychosocial support provided by implementation partners. | 2 | 2 | Promoting alternative livelihoods for the efficient use of available local resources with limited or no environmental risks Training to enable smallholder farmers to use environmentally friendly and climate-friendly options Promoting the use of locally adapted seeds, including the introduction of drought-tolerant plant varieties Involvement of community representatives when it comes to the concerns of returnees, internally displaced persons and the host community – using do-no-harm approaches. Using the positions of women's rights actors and civil society to support the development and modification of customary law Ensuring that women, the elderly, persons with disabilities and other vulnerable groups such as ethnic minorities are represented in the activities supported by the project Close and high-quality professional support of the implementation partners of psychosocial support |
| Corruption risks |  |  |  |
| Illegally diverted implementation resources Fiduciary risk in a context of corruption | 3 | 2 | The project has detailed risk management plans that have mechanisms for financial and compliance monitoring. The approach ensures that compliance is verified. The program emphasizes a zero-tolerance policy towards fraud Increased attention to transparency principles and close financial management, including the provision of adequate resources |
| Aggregate risk | 3 | 2 |  |

*) Levels: 1=low, 2=medium, 3=high, 4=very high

## 6.3	Certificate

After examining alternative options, the TC measure described and its implementation modalities correspond to the optimal relationship between the purpose pursued by the TC measure and the means to be used. The BMZ's country strategies and programmes as well as binding priority concepts and cross-sectoral strategies were taken into account in the planning.