| Name of the module Capacity Building in Education IV | Project number 2023.2271.7 | Duration 12/2024 to 11/2029 |
| --- | --- | --- |
| Country/Region/Global Ethiopia | Impact matrix created on 03.10.2025 |  |

| Objectives | Indicators | Definitions, data sources and data collection information |
| --- | --- | --- |
| EZ-Programmziel The income and employment situation for the Ethiopian population, especially for young people, has improved through demand-oriented training and qualification offers. | Development Cooperation Programme Objective Indicator 4 80% of the 100 representatively selected representatives of state and private vocational education and training institutions as well as the participating employers rated the capacity development in the vocational education and training sector by German development cooperation as either very beneficial or beneficial. Baseline: n/a Target value: 80, including 40 representatives of state and private vocational education and training institutions, 40 employer representatives from the private sector (2025) Actual value: 76 % (2023) Expected to be achieved within the projected timeframe: Yes | The baseline is collected as part of a tracer study. The target value is determined after the underlying value has been determined. (For the tracer study and for the establishment of an alumni network, a consultant is to be commissioned in the near future with funds from the BMZ's Study and Skilled Workers Fund.) |
| Assumptions for the achievement of the development cooperation programme objective | Describe here essential assumptions that are important for achieving the development cooperation programme goal. |  |
| Modulziel The reform to align Ethiopian vocational education and training with the needs of the labour market has been supported in its operationalization. | Module Target Indicator 1 An up-to-date vocational education and training strategy jointly developed by state and private vocational education and training stakeholders has been submitted to the Ministry of Labour and Skills (MoLS) for adoption. Baseline: 2 Vocational education and training strategies (there are vocational education and training strategies from 2008 and 2020, but they are either no longer valid (2008) or have not been adopted by the Cabinet (2020)) Target value: 3 Vocational education and training strategies (06/2026) Actual Value: | Evaluation of the submission of the final vocational education and training strategy in written form to the MoLS; Evaluation of the minutes of the MoLS Steering Group meeting in which the strategy was presented. evaluation of the documentation of the joint development by state and private educational actors; evidenced by draft strategies, annotated versions of strategies, minutes of meetings and committees. The strategy covers vocational education and training topics such as: vision, mission and goals; participation of the private sector in the design, planning and provision; federal (national and regional) system of rules and coordination of vocational education and training; gender-transformative and inclusive orientation; Requirements for alignment with medium-term social and economic transformation processes (sustainable economic activity; digitization); Specifications and process definitions for the development and quality of training standards. The state actors in vocational education and training include the MoLS and vocational education and training administrations of the 12 regions and 2 autonomous cities. Private VET actors include the Ethiopian Chamber of Commerce and Sectoral Associations (ECCSA), constituted business organisations at national level and in the regions. Date of data collection: 12/2025 |
|  | Module Target Indicator 2 A steering structure consisting of representatives of the responsible ministries, the regions and the organised private sector is functional. Baseline: 0 Control structures (coordination has so far only been carried out ad hoc via the MoLS, but not in a structured way) Target value: 1 Governance structure (11/2027) Actual Value: | Evaluation of the documentation of the meeting, committee and working group minutes of the steering structure. Governance structure means a cooperation structure in which the Ethiopian vocational education and training stakeholders meet regularly for professional exchange, discussions and decision-making. At national level, the group of ministries can include – in addition to the MoLS – the Ministry of Education, the Ministry of Industry, the Ministry of Agriculture, the Ministry of the Environment and other ministries that may be relevant for the content, planning and implementation of vocational education and training. Representatives of the regions are, for example, vocational training administrations of the 12 regions and the 2 autonomous cities. Representatives of the private sector include ECCSA and other organisations in the constituted economy at national and regional level, as well as leading sector companies. Functionality in the sense of the indicator means that the role (mandate; see Vocational Education and Training Strategy) and tasks (see Vocational Education and Training Strategy) are defined for the steering structure, there is a description of the process organisation and the communication processes, financial and human resources are available and the participants meet regularly. Data collection dates: 12/2026 and 11/2027 |
|  | Module Target Indicator 3 220 employees of the relevant state and private vocational education and training actors, 67 of whom are women, use an example to confirm that their skills in aligning vocational education and training with the needs of the green, digital and social transformation have improved. Baseline: 70 employees of state and private vocational education and training actors, 7 of whom are women Target value: 220 employees of state and private vocational education and training actors, 67 of whom are women (11/2027) Actual Value: | Evaluation of a survey of employees trained by the project with regard to improving their analytical, process, control and cooperation skills for green, digital and social transformation processes. Transformation processes are fundamental societal, social and economic processes of further development and realignment (e.g. green and digital transformation) that make it necessary to adapt the governance, content, methodologies, process and delivery mechanisms of vocational education and training. Green transformation includes the introduction of environmentally sustainable practices on the way to climate neutrality of the economy and society. The requirements of the green transformation include, for example, topics such as energy efficiency, the use of environmentally and climate-friendly working/production methods and materials, wastewater and waste management. Digital transformation includes the comprehensive introduction of digital knowledge transfer, production and administration processes. Societal transformation encompasses systemic changes in institutions, social norms, and power relations. Data collection dates: 12/2026 and 11/2027 |
|  | Module Target Indicator 4 An action plan on gender equality in vocational education and training, jointly developed by state and private vocational education and training stakeholders, is now available to the MoLS in its final version. Baseline: 0 Gender Action Plans (so far, gender equality in vocational education and training has not been promoted explicitly and in a structured way) Target value: 1 Gender Action Plan for Vocational Education and Training (12/2026) Actual Value: | Evaluation of the existence of the final action plan at the MoLS; Evaluation of the documentation of the joint development by the VET stakeholders; the joint development is evidenced by drafts, annotated versions of the action plan, minutes of meetings of the working group. Evaluation of the minutes of the meetings of the MoLS Steering Group with regard to the consideration of the action plan. The Action Plan on Gender Equality in Vocational Education and Training includes topics such as international and national gender policies and strategies in vocational education and training, as well as descriptions of the development of gender-responsive vocational education and training and the gender-responsive and/or gender-transformative implementation of vocational education and training, while specifying the gender-transformative objectives of the Vocational Education and Training Strategy; Guidelines for combating gender stereotypes; Recommendations for action to reduce the gap in care responsibilities and instruments for creating a supportive environment for women in vocational education and training, e.g. childcare, safe transport to the vocational training institution, part-time classes, women's classes, infrastructure for women (toilets, changing rooms, recreation rooms and breastfeeding rooms). Date of data collection: 12/2026 |
|  | Module Target Indicator 5 51% of young people in Ethiopia, of whom 50% are women and 10% are people with disabilities, have taken up paid or self-employed employment six months after the end of the measure. Baseline: 46% young people (of which 38% women, 0% people with disabilities) (02/2025) Target: 51% young people (of which 50% women, 10% people with disabilities) (11/2029) Actual Value: | "Young people" for the purposes of the indicator and as defined in Ethiopia include apprentices, jobseekers or informal workers aged 15-29. Own survey by determining and assessing employment prospects, employment status and income development within the framework of retention studies. Dates of data collection: six months after completion of a qualification measure, starting 11/2026. |
| Assumptions for achieving the module goal | The political will of the Ethiopian Government to implement the vocational education and training reform process will remain in place in the medium term and is backed by human and financial resources from the partner side. The Ethiopian Government's priorities regarding vocational education and training and its reform remain unchanged. The interest of the Ethiopian government and the organised private sector in greater involvement of the private sector in the governance of vocational education and training remains. The establishment of the MoLS, which is exclusively responsible for vocational education and training and labour market issues, will increase the financial resources for vocational education and training. Investments by other donors in the Ethiopian vocational education and training sector (World Bank, EU) are increasing. Various donor organisations coordinate their work in the field of vocational education and training in a structured manner. |  |
| Output 1 The legal and factual regulatory and control framework of the vocational education and training system has improved. | Output Indicator 1.1 A working group composed of key actors in vocational education and training, including the organised private sector and the regions, has agreed on the draft of an up-to-date vocational education and training strategy. Baseline: 0 drafts (there are no drafts yet) Target value: 1 draft (10/2025) Actual Value: | Evaluation of the minutes of the constituent meeting of the working group with regard to participating institutions and meeting contents. Key actors in vocational education and training are described in the sources for MZI 1. The contents of a vocational education and training strategy are described in the sources for MZI 1. Evaluation of the minutes of the final meeting of the working group on the development of an up-to-date vocational training strategy. United in the sense of the indicator means that vocational education and training stakeholders have signed a memorandum of understanding in which they confirm their approval of the draft vocational education and training strategy. Date of data collection: 10/2025 |
|  | Output Indicator 1.2 A concept of a steering structure for vocational education and training developed by key actors in vocational education and training has been adopted by the MoLS. Baseline: 0 concepts (coordination has so far only been carried out ad hoc via the MoLS, but not structured) Target value: 1 concept (03/2026) Actual Value: | Evaluation of the minutes of the meeting of the MoLS Steering Group in which the concept was adopted. Evaluation of the documentation of the preparation by the vocational training stakeholders with regard to the groups of participants involved in the conception, concept grades, annotated draft versions, minutes of meetings of working groups. In the sense of the indicator, accepted means that the MoLS Steering Group decides on measures of a legal, organisational or other nature to enable the implementation of the concept. The concept describes an institutionalised cooperation structure (forum, commission, permanent conference with secretariat, agency, etc.) between the actors in vocational education and training (national: national and regional; private). In accordance with the proposed structure, the concept makes statements about participants, responsibilities, committees, voting rights, processes and financing. |
| Output 2 The role of the private sector in the governance of the vocational education and training system has been strengthened. | Output Indicator 2.1 An ECCSA vocational training unit has been established with the involvement of chambers, associations and private sector companies. Baseline: 0 VET units (there is no VET unit in ECCSA yet) Target value: 1 vocational training unit (06/2026) Actual Value: | evaluation of the submission of the final concept in written form to the ECCSA Presidium (minutes of meetings) and written confirmation of the ECCSA Board's approval of the establishment of the VET unit; Evaluation of the documentation for the development of the concept by a working group of selected Chamber employees, representatives of Chamber member organisations and co-opted representatives of selected state vocational education and training actors with regard to the existence of draft concepts, annotated versions of the concept and minutes of meetings of the working group. The concept for an ECCSA vocational training unit, which has been approved by the Executive Board, includes points such as the role, objectives and tasks of the department; personnel and financial resources of the department; Organizational structure of and responsibilities in the department; Assignment of the department within ECCSA (reporting lines). The unit is established when the ECCSA Board has approved the concept for the establishment of a vocational training unit. Key actors in vocational education and training are described in the sources for MZI 1. Date of data collection: 06/2026 |
|  | Output indicator 2.2 11 Cooperative relationships between private and public actors in the vocational education and training sector at different levels (micro, meso, macro) have been established. Baseline: 2 cooperative relationships (2025) Target value: 11 cooperation relationships (11/2029) Actual Value: | Public actors include vocational schools, administrative units of vocational education and training in the regions and municipalities. Representatives of the private sector are, for example, the Ethiopian Chamber of Commerce and Sectoral Association (ECCSA), other organisations of the constituted economy at the respective levels, leading sector companies and small and medium-sized enterprises that want to provide training or participate in training. An enterprise is any entity, regardless of its legal form and the way in which it is financed, that carries out an (economic) activity consisting in offering a good or service on a market (cf. European Union definition). Cooperation relationships include regular learning and exchange formats and joint involvement in governance structures. A cooperative relationship is established when actors from the public and private sectors demonstrably cooperate or exchange information on a regular basis. This means that the cooperation goes beyond a one-time interaction. Data collection is carried out through separate surveys, using signed documents to formalise cooperation relationships (e.g. Memorandum of Understanding, MoU) or minutes of meetings to record cooperation relationships. Company data is collected disaggregated by sector, companies headed by women by means of surveys. Dates of data collection (06/2026, 06/2027, 06/2028, 06/2029) |
| Output 3 Vocational education and training stakeholders are in a position to align the vocational education and training system with social and economic transformation processes, including gender equality. | Output indicator 3.1 2 recommendations for action on the requirements of the digital and green transformation for vocational competence development, jointly developed by state and private vocational education and training stakeholders with the participation of selected companies, have been implemented. Baseline: 0 Recommendations for action (no recommendations for action by the above-mentioned actors regarding the digital and green transformation have yet been implemented) Target value: 2 recommendations for action (06/2027) Actual Value: | Evaluation of the existence of the final recommendations for action in written form at the MoLS; Evaluation of the documentation of the development of the recommendations for action with regard to the participation of state and private VET stakeholders and companies via draft recommendations, annotated versions of concepts, minutes of meetings of working groups (on the topics of digital and green transformation). Recommendations for action include the user-oriented compilation of ideas, processes, instruments and templates for the operational implementation of transformation measures. For the definition of transformation processes, see MZI 3. Recommendations for action are implemented if the responsible institutions have submitted signed reports on implementation and these have been checked for plausibility. Date of data collection: 06/2027 |
|  | Output Indicator 3.2 2 Support programmes for young female managers and currently active female managers in vocational education and training have been institutionalised. Baseline: 1 funding programme (so far there is only one funding initiative for female managers who are currently working) Target value: 2 funding programmes (12/2026) | Evaluation of the documentation of the concept of the funding programmes with regard to target group; Methods: Training and coaching; Contents; implementing organisation(s); Timeframe; Financing. Evaluation of the documentation of the registration of the 1st cohort of young female (junior) managers with regard to number, age, previous qualifications, current professional activity, institutional affiliation. Evaluation of the documentation of the continuation of the cohorts of currently active female managers in terms of number, age, previous qualifications, current professional activity, institutional affiliation, last professional career development. Institutionalized means (a) that a first cohort has been identified, selected, and a program has been started for young female leaders; (b) for current female managers, the programmes for existing cohorts have been continued; (c) MoLS has taken control of the program and (d) the Ministry of Public Service recognizes the program internally as an advancement qualification. In this context, young means people between the ages of 15 and 29. Data collection dates: 12/2025, 12/2026, 11/2027 |
| Output 4 The employability of the young people supported by the project has improved in cooperation with the private sector in relevant value chains and sectors, including the digital economy. | Output Indicator 4.1 3,350 trainees, job seekers or informal workers, including 2,320 women and 150 people with disabilities, have successfully completed a labour market-oriented qualification measure on green, digital and entrepreneurial skills developed together with the private sector. Baseline: 1,350 apprentices, jobseekers or informal workers (of which 720 women) (11/2024) Target value: 3,350 trainees, jobseekers or informal workers, of which 2,320 are women and 150 people with disabilities (06/2029) Actual Value: | Qualification measures include, for example, short-term technical training, cooperative training and training to teach entrepreneurial skills. Green skills refer to the knowledge, skills and abilities required to operate successfully in an increasingly sustainable economy. Successfully completed means that participant lists of the qualification measures carried out as well as participant certificates and documentation of the training implementation are available. Evaluation of the process documentation (protocols, reports, participants disaggregated) of the development of qualification measures with regard to the participation of the private sector. Data collection dates: 06/2026, 06/2027, 06/2028, 06/2029 |
|  | Output Indicator 4.2 400 companies in relevant value chains and sectors, including the digital economy, are involved in the development, adaptation or implementation of labour market-oriented qualification measures. Baseline: 186 companies (08/2025) Target value: 400 companies (06/2029) Actual: | An enterprise is any entity, regardless of its legal form and the way in which it is financed, that carries out an (economic) activity consisting in offering a good or service on a market (cf. European Union definition). The value chains and sectors are selected in the initial phase (inception phase) of EU combined financing on the basis of studies. Labour market-oriented qualification measures are, e.g. short-term technical training, cooperative training and training to impart entrepreneurial skills. "Integrated" means that the companies are either involved in the development or revision of the training measure or in its implementation, e.g. by taking on trainees in the company. Evaluation of the process documentation (protocols, reports, participants disaggregated) of the development of qualification measures with regard to the participation of companies. Dates of data collection: 06/2026, 06/2027, 06/2028; 06/2029 |
| Assumptions for the achievement of outputs | The Ethiopian central government is also prepared to allow regional governments and organisations in the constituted economy to participate in the development of policies and strategies for vocational education and training. Companies will continue to recognize the benefits of transformative business models (sustainable, digital) in the future and see the associated need to equip and employ employees with the appropriate skills. Young people and young adults will continue to be interested in high-quality vocational education and training in the future, are interested in the green transformation and digitalisation and the associated training and further education opportunities and take advantage of the offers. Ethiopian VET stakeholders consider gender equality in VET to be relevant. MoLS continues its strategy to digitize knowledge management and administrative processes. |  |

| Outputs | Key activities on outputs | Inputs / Planned Instruments |
| --- | --- | --- |
| Output 1 | - Strategic and technical advice to the MoLS and the regional vocational education and training administrations on the development and coordination of a vocational education and training strategy, a vocational education and training law and action plans for the respective implementation - Strategic and technical advice to the MoLS on the development and coordination of an action plan for gender equality in vocational education and training and on the establishment of gender-sensitive monitoring for the action plan - Strategic and technical advice to MoLS on the design of an institutionalised structure for the design, planning and management of vocational education and training - Implementation of competence development measures (e.g. trainings, coaching measures, etc.) for political decision-makers, management and technical staff of the national and regional vocational education and training administration - Expert advice to MoLS on linking data from HETMIS on the provision of vocational education and training with labour market data generated from the Labour Market Information System (LMIS) in close coordination with KfW - Advising the MoLS on the establishment of a coordination mechanism (structure, processes) for sectoral budget support by bilateral and multilateral development partners (incl. KfW Basket) | International LZFK (51 FKM) Nationale LZFK (297 FKM) KZE (27 FKM) Tangible goods EUR 170,720 |
| Output 2 | - Strategic and technical advice to ECCSA on the design and establishment of a vocational training department - Implementation of capacity and competence development measures for organizations in the constituted economy (trainings, roundtables, coaching, etc.) - Coordination of exchange formats between the regional vocational education and training administrations and the private sector in selected regions - Establish cooperation mechanisms to institutionalise private sector participation in vocational education and training in key areas, such as the design/updating of curricula, the development/updating of professional standards or assessment tools in selected sectors, among others | International LZFK (57 FKM) Nationale LZFK (441 FKM) KZE (132 FKM) Tangible goods EUR 220,720 Financing: EUR 770,000 |
| Output 3 | - Providing strategic and technical advice to MoLS on the establishment of exchange/coordination mechanisms with relevant ministries, regions and private sector partners - Implementation of capacity and competence development measures for political decision-makers, management and technical staff of the MoLS and regional vocational education and training administrations as well as organisations of the constituted economy to identify and control change processes in vocational education and training - Implementation and expansion of the programme "Women in Leadership Positions in Vocational Education and Training" as well as strategic and technical advice on the design and piloting of a programme "Young Female Managers for Vocational Education and Training" - Expert and process consulting for the development and implementation of digital and green recommendations for action in the vocational education and training sector - Strategic and technical advice on the (further) development and introduction of digital knowledge management and administrative systems for state vocational education and training stakeholders | International LZFK (35 FKM) Nationale LZFK (257 FKM) KZE (38 FKM) Material goods 99.008 EUR Financing: EUR 453,000 |
| Output 4 | - Conducting a situation analysis to understand the digital and entrepreneurial skills training programme offered by VET institutions and to assess the digital readiness and current accessibility of VET programmes and facilities for students with disabilities Strategic and technical advice to partners and other VET stakeholders and leading sector companies on the design and implementation of exemplary, innovative qualification measures on green, digital and entrepreneurial skills - Advising vocational education and training stakeholders on the design and implementation of inclusion-promoting and gender-responsive training measures - Advising the partner on the design and implementation of targeted outreach campaigns to attract female students to digital skills training and entrepreneurship programs. | International LZFK (99 FKM) Nationale LZFK (779FKM) KZE (91 FKM) Material goods 12,103 EUR Financing: EUR 2,127,000 |