## Slide 1: SKYE II PROCESS MAP
10.06.2025

## Slide 2
Who? Responsibility
What/Ressources
Activities/steps of M&E process Output 1.1
Trigger:
TA indicates that a PPDP session has taken place or RbM system indicates that minutes are due
Draw up of measures for demand-driven TVET or Employment Promotion
Technical Advisor
Submits filled tool, accompanying documents (MoV)
Fills & submits tool, accompanying documents
M&E Officer
Entering data into RbM system
Upload on RbM system

## Slide 3
Process Name |  |  |  | Process Owner |  | 
Draw up of measures for demand-driven TVET or Employment Promotion |  |  |  | M&E Officer |  | 
Purpose of Process |  |  |  |  |  | 
This process aims at understanding whether a sufficient number of measures has been drawn up as an output of GIZ´s support to the dialogue forum on federal and/or national level |  |  |  |  |  | 
Input | Supplier of Input |  | Main Activities / steps |  | Output | Recipient of Output
Meeting minutes and accompanying documents | Technical Advisor |  | Fills & submits tool, accompanying documents |  | Completed review and assessment | M&E Officer
Information via e-mail | Technical Advisor |  | Entering data into RbM system |  | Data entered into RbM system | GIZ project team (and project partners)
IT-System |  | Roles |  |  |  | 
RbM system in excel format |  | Process Owner = responsible for description of process and commissioning the Process Manager = M&E Officer Process Manager = responsible for implementation of the process = M&E Officer Process Employee = responsible for contributing specified tasks to the process = Technical Advisor |  |  |  | 
Potential for Improvement |  | Indicators |  |  |  | 
 |  | 18 measures by September 2026 |  |  |  | 
Profile of M&E process Output 1.1
Draw up of measures for demand-driven TVET or Employment Promotion

## Slide 4
Who? Responsibility
What/Ressources
Technical Advisor
Activities/steps of M&E process Output 1.2
Information to M&E Officer that a data package was discussed during the PPDP
Technical Advisor informs M&E Officer via e-mail that a data package was discussed during the PPDP.
Submits 1.2 tool, minutes of meeting and supporting MoVs.
Trigger:
Technical Advisor indicates that a Data-package has been submitted and discussed in the PPDP / RbM system indicates that Data-package is due
Draw up of measures for demand-driven TVET or Employment Promotion
M&E Officer
Entering data into RbM system
Upload on RbM system

## Slide 5
Process Name |  |  |  | Process Owner |  | 
Draw up of measures for demand-driven TVET or Employment Promotion |  |  |  | M&E Officer |  | 
Purpose of Process |  |  |  |  |  | 
This process aims to count the number of data packages/analyses that has been up for discussion during a PPDP session |  |  |  |  |  | 
Input | Supplier of Input |  | Main Activities / steps |  | Output | Recipient of Output
Information via email with accompanying documents | RbM system |  | Information to M&E Officer that a data package was discussed during the PPDP |  | Completed documents | M&E Officer
Completed documents | M&E Officer |  | Entering data into RbM system |  | Data entered into RbM system | GIZ project team (and project partners)
IT-System |  | Roles |  |  |  | 
RbM system in excel format |  | Process Owner = responsible for description of process and commissioning the Process Manager = M&E Officer Process Manager = responsible for implementation of the process = M&E Officer Process Employee = responsible for contributing specified tasks to the process = Technical Advisor |  |  |  | 
Potential for Improvement |  | Indicators |  |  |  | 
 |  | 4 members once a year by September 2026 |  |  |  | 
Profile of M&E process Output 1.2
Draw up of measures for demand-driven TVET or Employment Promotion

## Slide 6
Who? Responsibility
What/Ressources
Activities/steps of M&E process Output 2.1
Technical Advisor
Notifies M&E of ToT activity for TVET staff
TA fills Activity tracker and informs M&E Unit of activity via email.
Coherence of activity can be checked with M&E Unit if necessary.
Fills & submits tool, accompanying documents
Technical Advisor
Completes and returns filled tool, accompanying documents (MoV)
Trigger:
Technical Advisor reports that a ToT activity is scheduled to take place
No. of TVET teachers trained to improve the quality of education in accordance with NOS
M&E Officer
Validates completeness and enters into RbM
Upload on RbM system

## Slide 7
Profile of M&E process Output 2.1
Process Name |  |  |  | Process Owner |  | 
No. of TVET teachers trained to improve the quality of education in accordance with NOS |  |  |  | M&E Officer |  | 
Purpose of Process |  |  |  |  |  | 
To confirm that TVET Teachers received training aligned with the NOS-revised/developed curricula |  |  |  |  |  | 
Input | Supplier of Input |  | Main Activities / steps |  | Output | Recipient of Output
Information via e-mail | Technical Advisor |  | Notifies M&E of ToT activity for TVET staff |  | Information is noted. Coherence of activity is checked if necessary | M&E Officer
Submission of tool and accompanying documents via e-mail | Technical Advisor, Implementing partners |  | Fills & submits tool, accompanying documents |  | MoV that training had taken place | M&E Officer
Completed documents | M&E Officer |  | Validates completeness and enters into RbM |  | Data entered into RbM system | GIZ project team (and project partners)
IT-System |  | Roles |  |  |  | 
RbM system in excel format |  | Process Owner = responsible for description of process and commissioning the Process Manager = M&E Officer Process Manager = responsible for implementation of the process = M&E Officer Process Employee = responsible for contributing specified tasks to the process = Technical Advisor |  |  |  | 
Potential for Improvement |  | Indicators |  |  |  | 
 |  | 360 Teachers (108 women) by September 2026 |  |  |  | 
No. of TVET teachers trained to improve the quality of education in accordance with NOS

## Slide 8
Who? Responsibility
What/Ressources
Technical Advisor
Activities/steps of M&E process Output 2.2
Institution confirms implementation and informs TA
Technical Advisor informes M&E Officer that NOS-based trainings took place and provides NOS names
M&E Officer
Data entry into RbM
Technical Advisor
Curriculum outlines, participant lists, time table, site visit,
Technical Advisor
Data collection tool, filling in of data collection tool and sending it to M&E Officer
Conduction of site visits / request of evidence
Preparing data collection for M&E Officer
M&E Officer
Checking and informing Technical Advisor about completeness or request for additional information
Trigger:
Focal persons at institution indicate NOS-based courses have commenced / RbM asks focal points about NOS-based courses
1 week
2 weeks
2 weeks
2 days
1 week
No. of TVET institutions adopting at least 2 new training standards
Upload on RbM system
Checking of completed 2.2 data collection tool and informing TA

## Slide 9
Profile of M&E process Output 2.2
Process Name |  |  |  | Process Owner |  | 
No. of TVET institutions adopting at least 2 new training standards |  |  |  | M&E Officer |  | 
Purpose of Process |  |  |  |  |  | 
To confirm that partner TVET institutions are delivering at least 2 NOS-based trainings |  |  |  |  |  | 
Input | Supplier of Input |  | Main Activities / steps |  | Output | Recipient of Output
Institution records | Focal Person at institution |  | Institution confirms implementation |  | Number and names of NOSs | Technical Advisor
Curriculum outlines, participant lists, time table, site visit results | Focal Persons |  | Conduction of site visits / request of evidence |  | Complete data and evidence collection | Technical Advisor
Complete data and evidence collection | Technical Advisor |  | Preparing data collection for M&E Officer |  | Filled in data collection tool | M&E Officer
Filled in data collection tool | Technical Advisor |  | Checking of completed 2.2 data collection tool and informing TA |  | Finalized completeness check | Technical Advisor
Finalized completeness check | M&E Officer |  | Entering data into RbM system |  | Data entered into RbM system | GIZ project team (and project partners)
IT-System |  | Roles |  |  |  | 
RbM system in excel format |  | Process Owner = responsible for description of process and commissioning the Process Manager = M&E Officer Process Manager = responsible for implementation of the process = M&E Officer Process Employee = responsible for contributing specified tasks to the process = Technical Advisor |  |  |  | 
Potential for Improvement |  | Indicators |  |  |  | 
 |  | 15 Institutions by September 2026 |  |  |  | 
No. of TVET institutions adopting at least 2 new training standards

## Slide 10
Who? Responsibility
What/Ressources
Activities/steps of M&E process Output 3.1
Technical Advisor
Reports launch and operation status
Sends in commissioning documents (media report & photos)
Technical Advisor
3.1 Tool, accompanying documents (MoV)
Submits completed 3.1 tool and accompanying documents (MoV)
Checking of completed 3.1 data collection tool and informing TA
M&E Officer
Checking and informing Technical Advisor about completeness or request for additional information
Trigger:
Technical Advisor flags that a new job centre has been launched and in operation.
No. of jobs centres in operation
M&E Officer
Upload on RbM system
Data entry into RbM

## Slide 11
Profile of M&E process Output 3.1
Process Name |  |  |  | Process Owner |  | 
No. of jobs centres in operation |  |  |  | M&E Officer |  | 
Purpose of Process |  |  |  |  |  | 
To confirm that newly launched Job Centres are functional and have met indicator requirements |  |  |  |  |  | 
Input | Supplier of Input |  | Main Activities / steps |  | Output | Recipient of Output
Information via e-mail | Technical Advisor |  | Reports launch and operation status |  | Information via e-mail, MoV | M&E Officer
3.1 tool and Accompanying documents | Technical Advisor |  | Submits completed 3.1 tool and accompanying documents (MoV) |  | Information via e-mail | M&E Officer
3.1 tool and Accompanying documents | Technical Advisor |  | Checking of completed 3.1 data collection tool and informing TA |  | Completed documents | M&E Officer
Completed documents | M&E Officer |  | Data entry into RbM |  | Data entered into RbM system | GIZ project team (and project partners)
IT-System |  | Roles |  |  |  | 
RbM system in excel format |  | Process Owner = responsible for description of process and commissioning the Process Manager = M&E Officer Process Manager = responsible for implementation of the process = M&E Officer Process Employee = responsible for contributing specified tasks to the process = Technical Advisor |  |  |  | 
Potential for Improvement |  | Indicators |  |  |  | 
 |  | 38 job Centres by September 2026 |  |  |  | 
No. of jobs centres in operation

## Slide 12
Who? Responsibility
What/Ressources
Activities/steps of M&E process Output 3.2
Focal person JC / TA
JC Focal person submits monthly JC report. Notification from TA of an ALMM activity
M&E Officer receives the JC Excel report via email.
Technical Advisor gives further details about activity via email and activity tracker
M&E Officer
M&E Officers goes through data before uploading
Data cleaning & validation
Trigger:
Monthly reporting due from JCs or Notification of ALMM from TA
No of job seekers who find employment through enhanced services
M&E Officer
Upload on RbM system
Data entry into RbM

## Slide 13
Profile of M&E process Output 3.2
Process Name |  |  |  | Process Owner |  | 
No of job seekers who find employment through enhanced services |  |  |  | M&E Officer |  | 
Purpose of Process |  |  |  |  |  | 
To confirm how many job seekers benefited from ALMMs |  |  |  |  |  | 
Input | Supplier of Input |  | Main Activities / steps |  | Output | Recipient of Output
Monthly JC ALMM data | Technical Advisor |  | JC Focal person through the TA submits monthly JC report. Notification from TA of an ALMM activity |  | Information (excel sheet) via e-mail | M&E Officer
Excel data sheet | Technical Advisor |  | Data cleaning & validation |  | Clean and complete data | M&E Officer
Clean and complete data | M&E Officer |  | Data entry into RbM |  | Data entered into RbM system | GIZ project team (and project partners)
IT-System |  | Roles |  |  |  | 
RbM system in excel format |  | Process Owner = responsible for description of process and commissioning the Process Manager = M&E Officer Process Manager = responsible for implementation of the process = M&E Officer Process Employee = responsible for contributing specified tasks to the process = JCs & Technical Advisor |  |  |  | 
Potential for Improvement |  | Indicators |  |  |  | 
Introduce Kobo tool for Jobfairs |  | 28,200 (14,100) Nigerian Job seekers by September 2026 |  |  |  | 
No of job seekers who find employment through enhanced services

## Slide 14
Who? Responsibility
What/Ressources
Activities/steps of M&E process Output 4.1
Technical Advisor
The institution shares with the TA an update on integration of content
Draft curriculum, revised module guide, approval letter
Technical Advisor
4.1 Tool, MoV
Completes checklist with institution, Submits completed 4.1 tool and supporting MoVs
Validates completeness and enters into RbM
M&E Officer
Upload on RbM system
Trigger:
Technical Advisor flags that new training content has been developed or integrated
No. of institutions in operation that have revised or added practical, gender-sensitive content to their teacher training courses

## Slide 15
Profile of M&E process Output 4.1
Process Name |  |  |  | Process Owner |  | 
No. of institutions in operation that have revised or added practical, gender-sensitive content to their teacher training courses |  |  |  | M&E Officer |  | 
Purpose of Process |  |  |  |  |  | 
To verify the integration of practical, demand-driven content in teacher training institutions |  |  |  |  |  | 
Input | Supplier of Input |  | Main Activities / steps |  | Output | Recipient of Output
Revised/Added content documentation | Technical Advisor |  | The institution shares with the TA an update on integration of content |  | Sumitted MoVs containing verified institutions with integrated training content (information via e-mail) | M&E Officer
MoVs | Technical Advisor |  | Completes checklist with institution, Submits completed 4.1 tool and supporting MoVs |  | Completed documents | M&E Officer
Completed documents | M&E Officer |  | Validates completeness and enters into RbM |  | Data entered into RbM system | GIZ project team (and project partners)
IT-System |  | Roles |  |  |  | 
RbM system in excel format |  | Process Owner = responsible for description of process and commissioning the Process Manager = M&E Officer Process Manager = responsible for implementation of the process = M&E Officer Process Employee = responsible for contributing specified tasks to the process = JCs & Technical Advisor |  |  |  | 
Potential for Improvement |  | Indicators |  |  |  | 
 |  | 2 relevant institutions by September 2026 |  |  |  | 
No. of institutions in operation that have revised or added practical, gender-sensitive content to their teacher training courses

## Slide 16
Who? Responsibility
What/Ressources
Activities/steps of M&E process Output 4.2
Technical Advisor
4.2 Tool, MoVs, Enrollment statistics & lists of training events for career counsellors
Completes checklist with institution, Submits completed 4.1 tool and supporting MoVs
Validates completeness and enters into RbM
M&E Officer
Upload on RbM system
Trigger:
Technical Advisor reports the setup of the sustainable training system for career counsellors is in place in a new state
No. of states that have introduced a sustainable training system for career counsellors
Notes: State MOU, ToT design

## Slide 17
Profile of M&E process Output 4.2
Process Name |  |  |  | Process Owner |  | 
No of states that have introduced a sustainable training system for career counsellors |  |  |  | M&E Officer |  | 
Purpose of Process |  |  |  |  |  | 
To confirm the rollout of sustainable training structure for career advisors in 4 states |  |  |  |  |  | 
Input | Supplier of Input |  | Main Activities / steps |  | Output | Recipient of Output
Documentation of a training system | Technical Advisor |  | Completes checklist with institution, Submits completed 4.1 tool and supporting MoVs |  | Sumitted MoVs containing sustainable training system (information via e-mail) | M&E Officer
Completed documents | M&E Officer |  | Validates completeness and enters into RbM |  | Data entered into RbM system | GIZ project team (and project partners)
IT-System |  | Roles |  |  |  | 
RbM system in excel format |  | Process Owner = responsible for description of process and commissioning the Process Manager = M&E Officer Process Manager = responsible for implementation of the process = M&E Officer Process Employee = responsible for contributing specified tasks to the process = JCs & Technical Advisor |  |  |  | 
Potential for Improvement |  | Indicators |  |  |  | 
 |  | 4 Federal States by September 2026 |  |  |  | 
No of states that have introduced a sustainable training system for career counsellors

## Slide 18
Who? Responsibility
What/Ressources
Activities/steps of M&E process Output 5.1
Technical Advisor
Reports company engagement activity
MOU between Private companies & TVET institution
Technical Advisor
5.1 Tool, MoVs
Completes checklist with tool, Submits completed 5.1 tool and supporting MoVs
Validates completeness and enters into RbM
M&E Officer
Upload on RbM system
Trigger:
Technical Advisor reports company involvement in a TVET activity
No. of private companies participating in activities with vocational institutions.
No. of activities carried out by vocational institutions with private sector partners

## Slide 19
Profile of M&E process Output 5.1
Process Name |  |  |  | Process Owner |  | 
No of private companies participating in no of activities that improve transition of school to work |  |  |  | M&E Officer |  | 
Purpose of Process |  |  |  |  |  | 
To improve transition of school to work |  |  |  |  |  | 
Input | Supplier of Input |  | Main Activities / steps |  | Output | Recipient of Output
Information via e-mail | Technical Advisor |  | Reports company engagement activity |  | Information is noted. Coherence of activity is checked if necessary | M&E Officer
Submission of tool and accompanying documents via e-mail | Technical Advisor |  | Completes checklist with tool, Submits completed 5.1 tool and supporting MoVs |  | MoV that training had taken place | M&E Officer
Completed documents | M&E Officer |  | Validates completeness and enters into RbM |  | Data entered into RbM system | GIZ project team (and project partners)
IT-System |  | Roles |  |  |  | 
RbM system in excel format |  | Process Owner = responsible for description of process and commissioning the Process Manager = M&E Officer Process Manager = responsible for implementation of the process = M&E Officer Process Employee = responsible for contributing specified tasks to the process = JCs & Technical Advisor |  |  |  | 
Potential for Improvement |  | Indicators |  |  |  | 
 |  | 200 private companies in 20 activities by September 2026 |  |  |  | 
No of private companies participating in no of activities that improve transition of school to work

## Slide 20
M&E Functions
Steering (Political, Operational, Ad-Hoc)
Organizing
Project documents and Updates
Knowledge Management
Sustainability Strategy
Planning and Tracking
OP/Biannual review of achievements
Annual progress/Targets
Reporting
MEL Plan
Annual report to BMZ
Biannual report DEZA
Quarterly progress report
Data collection and Validation
Continuous improvement
Good practices
Key M&E Processes