Annex 1: Results matrix of the module

Title of the TC module

A circular economy in Indonesia (InCircular) Country/region/global

Indonesia

Project no. 2024.2082.6

Results matrix created on

5 March 2025

Term

April 2025 to March 2029

| Goals | Indicators | Sources and time of data collection | Assumptions |
| --- | --- | --- | --- |
| DC programme objective Waste reduction and management in Indonesia have been improved in line with the principles of a circular economy and taking into account social implications, climate goals and national development plans. (Provisional) | The programme objective indicators have not yet been defined and will be added once the programme has been drafted. |  | Please leave blank |
| Module objective For three recyclables streams – packaging, residual waste and waste electrical and electronic equipment – implementation of the Circular Economy Roadmap in Indonesia has improved as a result of coordinated action on the part of public and private sector actors. | Module objective indicator 1 The number of agreements to implement the Circular Economy Roadmap for packaging, residual waste and waste electrical and electronic equipment concluded between public and private sector actors. Baseline value: No agreements (responsibilities have been defined in the Roadmap but not yet assumed) (September 2024) Target value: 3 agreements, 1 per recyclables stream (April 2026) | Evaluation of documents of the Ministry for National Development Planning (Badan Perencanaan Pembangunan Nasional, Bappenas) on implement-tation of the Circular Economy Roadmap/CE Roadmap), including minutes of meetings and declarations of intent between public and private sector actors (April 2026). Agreements on roles and responsi-bilities of actors and strategies for public monitoring and involvement of informal actors, e.g. for primarily collection and separation of recyclables for the complete value chain for three | The political framework ensures adequate continuity to be able to gradually implement waste management in the way required by a circular economy. |

1

A circular economy in Indonesia (InCircular)

Project no. 2024.2082.6

| Goals | Indicators | Sources and time of data collection | Assumptions |
| --- | --- | --- | --- |
|  |  | recyclables streams (packaging, residual waste and waste electrical and electronic equipment). Public actors include, for example, Bappenas, the Ministry of Environment (MoE), the Ministry of Industry (MoInd), the Ministry of Home Affairs (MoHA), National Research and Innovation Agency (Badan Riset dan Inovasi Nasional, BRIN), the National Public Procurement Agency (LKPP) (Lembaga Kebijakan dan Pengadaan Barang/Jasa Pemerintah, LKPP) and provincial and municipal administrations. Private sector actors include industry and trade associations, chambers of trade and commerce, producers of consumer goods and equipment, packaging manufacturers, retailers, waste management and recycling businesses and NGOs working in the field of solid waste management and the circular economy. The CE Roadmap defines indicators for the introduction of a circular economy and designates actors to implement it. However, sufficient agreement on roles has not yet been reached and responsibilities for particular issues have not been confirmed by all relevant actors. |  |

2

A circular economy in Indonesia (InCircular)

Project no. 2024.2082.6

| Goals | Indicators | Sources and time of data collection | Assumptions |
| --- | --- | --- | --- |
|  | Module objective indicator 2 The number of formal proposals for a statutory regulation of expanded producer responsibility for packaging that the MoE has submitted to the responsible body for review. Baseline value: No proposals (currently no statutory expanded producer responsibility for packaging, which has to date resulted in producers not assuming responsibility for collecting and recycling the packaging waste they generate). (September 2024) Target value: 1 proposal (December 2028) | Evaluation of the proposal for statutory regulation of extended producer responsibility (EPR) for packaging based on binding criteria for packaging producers regarding design, return, recycling and financing (December 2028). Proposals for statutory regulation of an EPR system are developed in collaboration with public and private sector actors and include setting up a national body to coordinate EPR implementation, reporting on packaging placed on the market, levying of fees on packaging used, distribution of fees across municipal or private waste collection, and development of guidelines for better packaging design. There are currently no formal proposals on EPR because the CE Roadmap was not adopted until early 2024 and has not yet been implemented. The Ministry of Justice and Human Rights will probably be responsible for reviewing the proposal. |  |

3

A circular economy in Indonesia (InCircular)

Project no. 2024.2082.6

| Goals | Indicators | Sources and time of data collection | Assumptions |
| --- | --- | --- | --- |
|  | Module objective indicator 3 The number of approaches to improving collection and recycling of retail packaging jointly implemented by public and private sector actors in Bali and East Java. Baseline value: No approaches (only isolated initiatives by NGOs) (September 2024) Target value: 1 approach (June 2028) | Surveys on volume, quality and price for retail packaging collected for recycling before (September 2026) and after (June 2028) implementation. The improvement methods include more efficient primary collection, improved quality of the retail packaging collected, treatment of materials that are difficult to recycle, and involvement of informal waste collectors. Individual initiatives that have already been implemented, such as the Alliance to End Plastic Waste will be analysed and where appropriate integrated or developed further. The public and private sector actors involved are provincial and municipal administrations, operators of waste collection depots, recycling companies, producers of packaging and appliances, retailers and tourist organisations. Joint implementation or development means that public and private sector actors coordinate closely when planning and implementing approaches. |  |

4

A circular economy in Indonesia (InCircular)

Project no. 2024.2082.6

| Goals | Indicators | Sources and time of data collection | Assumptions |
| --- | --- | --- | --- |
| Output 1 Bappenas’ institutional capacities with regard to steering the process of implementing the CE Roadmap for three recyclables streams – packaging, residual waste and waste electrical and electronic waste – have been improved with the involvement of women managers. | Output indicator 1.1 The number of formal multi-stakeholder forums to implement the CE Roadmap for three recyclables streams – packaging, residual waste and waste electrical and electronic waste – that have been set up by Bappenas. Baseline value: No formal multi-stakeholder forums (there have only been ad-hoc dialogue forums to date) (September 2024) Target value: 3 formal multi-stakeholder forums have been set up (December 2025) | Evaluation of attendance lists and minutes of meetings of each of the multi-stakeholder forums and their establishment by Bappenas (December 2025). Participants at multi-stakeholder forums include representatives of the government agencies responsible, industrial companies, business associations, the retail trade, producers and consumer groups. Formal means that the multi-stakeholder forums agree on a format of consultation, steering structure, number and selection of members and that they meet at regular intervals – at least twice a year. The subject matter dealt with is packaging, residual waste and waste electrical and electronic waste. | Bappenas has stressed its ambitions to act as coordinator and is actively seeking dialogue with relevant actors to drive forward implementation of the CE Roadmap. Bappenas confines its activities to political steering of implementation of the CE Roadmap and respects the responsibilities accorded to the line ministries MoE, MoInd and MoHA. Public and private sector actors contribute in participation processes and are able to agree on roles and responsibilities to implement the CE Roadmap in the three recyclables streams – packaging, residual waste and waste electrical and electronic waste. Ministries and industry participate and agree on guidelines for the introduction of a statutory EPR system for packaging. The development of legal and strategic requirements can succeed if there is close consultation with industry and the public through public consultation processes. Relevant actors in the packaging industry are actively involved in research and development with a view to producing common standards. Public and private sector actors in Bali are able to agree on an approach to improving collection and recycling of plastic bottles and support its implementation to an adequate degree. |
|  | Output indicator 1.2 The number of women professionals who have confirmed that participation in a training programme run by the academy for leadership in the circular economy increased their influence on implementation of the CE Roadmap Baseline value: 0 women professionals (the influence of women on the design of policy instruments in Bappenas is weak, since they lack access to decision-making functions and corresponding networks). (September 2024) Target value: 30 women professionals (September 2028) | Own survey using standardised questionnaires before participation in the training (December 2025) and on completion of the training programme (September 2028). The survey uses a scale of 1 to 5 (1 = no influence on implementation, 5 = great influence on implementation). The influence is confirmed only if there is a 2-point increase or higher. Greater influence means that the women who participated in the training programme have actively taken part in or led working groups or committees working on implementing |  |

A circular economy in Indonesia (InCircular)

Project no. 2024.2082.6

| Goals | Indicators | Sources and time of data collection | Assumptions |
| --- | --- | --- | --- |
|  |  | the CE Roadmap in their organisations. The academy can, for example, be attached to an existing training institution. | Improvement of municipal waste management can only be achieved in the long term through higher levels of funding for the local level, for example through cross-financing from EPR systems. The use of substitute fuels in the cement industry is accepted by legislators, municipalities, the waste management industry and the cement industry. Public procurement offices are prepared to integrate sustainability criteria into their procurement processes. |
| Output 2 The legal and strategic frameworks for introducing a circular economy for three recyclables streams – packaging, residual waste and waste electrical and electronic equipment – have been improved. | Output indicator 2.1 The number of public consultation processes to develop binding EPR legislation for packaging. Baseline value: 0 public consultation processes (The EPR legislation process has not yet formally started, public consultations to develop legislation are seldom used.) (September 2024) Target value: 1 public consultation process (March 2028) | Six-monthly evaluation of public documents of the environment ministry on consultation for binding EPR legislation for packaging (from July 2026). The public consultation process begins with the publication of a timetable for developing the legislation by MoE, including dates for involving other ministries and civil society. Implemented means that comments submitted have been documented and MoE’s responses are publicly available. |  |
|  | Output indicator 2.2 The number of strategies for monitoring recycling of waste electrical and electronic equipment agreed. Baseline value: No strategy (various documents on dealing with waste electrical and electronic equipment are available.) (September 2024) Target value: 1 strategy agreed (March 2027) | Evaluation of the strategy, including a plan of action, for monitoring recycling of waste electrical and electronic equipment, including documentation of the consultation process (March 2027). Monitoring recycling involves checking that treatment and recycling of waste electrical and electronic equipment, including disposal of residual material, is environmentally sound and complies with occupational safety regulations. Consultation means that the actors involved agreed on the strategy and action plan |  |

6

A circular economy in Indonesia (InCircular)

Project no. 2024.2082.6

| Goals | Indicators | Sources and time of data collection | Assumptions |
| --- | --- | --- | --- |
|  |  | in a formal process that was transparently documented. The actors responsible are primarily producers, retailers and importers, along with representatives of MoE, MoInd, MoHA, and selected provincial and municipal administrations. |  |
| Output 3 Cooperation on introducing a circular economy between government agencies and industry has been strengthened. | Output indicator 3.1 The number of uniform standards on waste reduction, reuse and recycling of product packaging that have been developed by the responsible government agencies in conjunction with industry. Baseline value: No standards (so far manufacturers and producers of packaging have only implemented corporate social responsibility activities, for example in the field of recycling or minimum recycled material content. There are no activities to reduce waste reduction or reuse packaging.) (September 2024) Target value: 3 standards (September 2027) | Evaluation of the standards on priority product packaging developed jointly by government agencies and industry, including documentation of the selection and consultation processes used during the development of uniform standards (September 2027). The government agencies primarily responsible are MoE, MoInd and BRIN. Industry includes representatives of product manufacturers and packaging companies, organisations and businesses from the field of waste collection and recycling, and possibly industry associations. In terms of content, the focus will be on uniform standards on dealing with packaging that contributes significantly to waste generation and has low recycling potential (for example, multi-layer plastic packaging, films, and containers made of mixed plastics). The standards are based on recognised examples of international best practice, but may also go beyond |  |

7

A circular economy in Indonesia (InCircular)

Project no. 2024.2082.6

| Goals | Indicators | Sources and time of data collection | Assumptions |
| --- | --- | --- | --- |
|  |  | the way single-use packaging works and focus on waste reduction and the potential for reusing resources. Uniform refers to packaging used in the same product groups (e.g. plastic bottles, packaging for food, cosmetics, and hygiene and household products) with regard to requirements that make collection, reuse and recycling easier. |  |
|  | Output indicator 3.2 The number of strategies agreed upon by the actors involved on using RDF. Baseline value: No strategies agreed (there are a number of studies and surveys, including some carried out by FC projects, but there is no sector-wide strategic guideline on improving the use of substitute fuels). (September 2024) Target value: 1 strategy agreed (March 2027) | Evaluation of the strategy for using RDF in the cement industry and plan of action (March 2027), including minutes of the consultation process between actors to ascertain their participation in drafting the strategy and their participation in exchange formats. Participating actors include representatives of the cement industry, the waste management and recycling industry and the regulatory authorities. Consultation means that the actors involved agreed on specific measures within the strategy that was developed. |  |

8

A circular economy in Indonesia (InCircular)

Project no. 2024.2082.6

| Goals | Indicators | Sources and time of data collection | Assumptions |
| --- | --- | --- | --- |
| Output 4 The technical capacities of provincial and municipal administrations to plan and report on measures in waste management and the circular economy have been strengthened. | Output indicator 4.1 The number of partner municipalities in the pilot provinces of East Java and Bali that have shared digitalised data on recycling of packaging waste based on uniform standards with the national level. Baseline value: 0 partner municipalities (no standardised reporting, due to a lack of capacities; municipalities report only when requested to do so by the national level.) (September 2024) Target value: 10 partner municipalities (December 2028) | Evaluation of data transfer reports on packaging waste from partner municipalities to the national level (six-monthly from December 2026), including review of standards, data quality and digital formats. Digitalised data include the type of recycling of packaging waste, as well as location and volumes, especially for plastics, cardboard, paper, metal and glass. Selection of the partner municipalities is based, for example, on what recycling infrastructure they have and their capacities. Uniform standards are defined in the Indonesian Government’s One Data policy on recording and sharing waste management data. |  |
|  | Output indicator 4.2 The number of project proposals developed on expanding existing waste treatment plants in East Java and Bali to enable them to produce RDF. Baseline value: No proposals (currently only isolated studies and surveys) (September 2024) Target value: 12 partner proposals (December 2028) | Evaluation of project proposals for financing that were submitted to the national budged or to development banks to ascertain compliance with the technical and financial requirements (December 2028). Project proposals contain information on sales markets in the cement industry for the substitute fuels produced, purchaser’s requirements in terms of quality and quantity |  |

9

A circular economy in Indonesia (InCircular)

Project no. 2024.2082.6

| Goals | Indicators | Sources and time of data collection | Assumptions |
| --- | --- | --- | --- |
|  |  | of the substitute fuels, consultation with municipalities and provision of land needed, along with a rough cost estimate. Existing waste treatment plants include landfills with facilities to separate out recyclables and composting facilities that have been financed by German FC or development banks. |  |
| Output 5 The strategic and technical requirements in public procurement of certain materials and equipment with regard to their social and environmental sustainability have been improved. | Output indicator 5.1 The number of strategies to take social and environmental sustainability into account in public procurement agreed between LKPP and MoE. Baseline value: No strategies agreed (a number of isolated sustainable procurement processes have been developed). (September 2024) Target value: 1 strategy agreed (June 2027) | Evaluation of the strategy to improve sustainable public procurement with regard to social and environmental sustainability criteria, including minutes of the consultation process between LKPP and MoE. Sustainable public procurement means that, for materials and equipment procured by public sector bodies, the sole criteria for making a decision are not price and quality but also social and environmental sustainability (e.g. whether something can be recycled or repaired). Consultation means that the actors involved have agreed on specific measures within the strategy that was developed so that sustainability criteria can in future be integrated into all public tender procedures, including any legislative changes required to do so. |  |

10

A circular economy in Indonesia (InCircular)

Project no. 2024.2082.6

| Goals | Indicators | Sources and time of data collection | Assumptions |
| --- | --- | --- | --- |
|  |  | Public procurement can be practised by various national and provincial administrative institutions, but is initially expected from key actors such as LKPP, MoE, Bappenas or MoHA. |  |
|  | Output indicator 5.2 The number of public procurement staff members who have successfully completed a training module in sustainable public procurement for selected materials and equipment. Baseline: 0 staff members (to date there have been only isolated training activities on sustainable procurement, carried out by previous projects. They did not focus on public procurement staff but on building capacity at LKPP.) (September 2024) Target value: 100 staff members (December 2027) | Evaluation of the number of staff members successfully completing the training modules and the lists of participants (December 2027). Successfully completed means that graduates have demonstrated competencies acquired in a standardised exam procedure. The institutions participants may come from are public procurement bodies such as ministries or government agencies at national or local level that regularly issue public invitations to tender. The training module includes selection of training institutions, development of training materials recognised for certification, training of trainers, and piloting the training module. Training modules are offered in two formats: face-to-face and online. |  |

11

A circular economy in Indonesia (InCircular)

Project no. 2024.2082.6

| Outputs | Key activities for outputs | Inputs/planned instruments | Assumptions |
| --- | --- | --- | --- |
| Output 1 |  Setting up multi-stakeholder forums for three recyclables streams – packaging, residual waste and waste electrical and electronic waste  Analysis of needs to harmonise legislation to promote a circular economy for three recyclables streams – packaging, residual waste and waste electrical and electronic equipment  Developing and piloting a circular economy training module focusing on women managers  Developing a monitoring procedure to check implementation of the CE Roadmap for packaging, residual waste and waste electrical and electronic equipment, taking into account the One Data guideline on evidence-based policy-making Improving sharing of information on ongoing and planned circular economy projects, including monitoring and coordinating interventions | International long-term experts National long-term experts Materials and equipment | Relevant actors can be involved in multi-stakeholder forums and participate proactively in steering the CE Roadmap for the selected recyclables streams: packaging, residual waste and waste electrical and electronic equipment. A suitable organisation such as a training institute can be recruited to host the academy for leadership in the circular economy. Industry supports promotion of waste reduction, reuse and recycling for products packaging, including cooperation across manufacturers, research institutes and government monitoring agencies. Partner municipalities have sufficient HR capacities to prepare and share regular reports on recycling of packaging waste. Waste recyclers in East Java and Greater Jakarta are prepared to share information on their technical and organisation capacities and to report on volumes recycled and also on residual waste that cannot be recycled. |
| Output 2 |  Consultation with relevant actors to develop legislation to gradually introduce statutory EPR for packaging materials, including sanctioning mechanisms and responsibilities for implementation  Involving civil society, along with awareness-raising activities in schools including social media campaigns (linked to Output 4)  Promoting international and regional exchange of knowledge on EPR implementation (in collaboration with German DC’s ASEAN projects)  Development of a strategy with action plan for monitoring recycling of waste electrical and electronic equipment | International long-term experts National long-term experts Short-term experts Materials and equipment |  |
| Output 3 |  Development and implementation of standards for better packaging design aiming to reduce and recycle waste and make it easier to recycle | International long-term experts National long-term experts Short-term experts |  |

A circular economy in Indonesia (InCircular)

Project no. 2024.2082.6

|  |  Promoting cooperation between industry, the retail trade, civil society and the regulatory authority (MoE) during the development and introduction of statutory EPR  Organising a dialogue on technology between Indonesian, regional and European industry around packaging innovations in collaboration with a leading institute for Process Engineering and Packaging and Indonesia’s National Research and Innovation Agency BRIN  Development of a strategy for using refuse-derived fuel in cement factories  Promoting an exchange of information between the Indonesian and the international cement industry on use of substitute fuels (building on the experience of the strategic alliance between GIZ and the cement industry) | Financing Materials and equipment |  |
| --- | --- | --- | --- |
| Output 4 |  Carrying out analyses of material streams and market analyses of packaging waste in East Java and Bali, including compiling lists of plants that can treat these types of waste  Recording and digitally sharing data on recycling of packaging waste in partner municipalities in East Java and Bali in line with uniform national standards  Capacity development for operators of local waste collection centres in East Java and Bali, including improving marketing and logistics for recovered recyclables  Development of measures for improved collection and recovery of retail packaging in Bali and East Java  Developing project proposals (to be financed by the government budget or development banks) for expanding existing waste treatment plants in East Java and Bali to enable them to produce RDF | International long-term experts National long-term experts Short-term experts Financing Materials and equipment |  |
| Output 5 |  Analysis of existing legislation with regard to sustainable public procurement | International long-term experts |  |

13

A circular economy in Indonesia (InCircular)

Project no. 2024.2082.6

|  |  Development of a strategy to improve sustainable public procurement, including policy recommendations and allocation of institutional responsibilities  Collaborating with LKPP and MoE on an analysis of overall life-cycle costs for selected products  Developing LKPP’s capacities with regard to ability to advise government institutions on sustainable public procurement Development of a training module for procurement staff, including training trainers at a recognised training institution | National long-term experts Materials and equipment |  |
| --- | --- | --- | --- |